## Summary
StayRelay 1,100-task production and quality plan
TASK-1000 opens controlled production; TASK-1100 certifies the stable polished website.
Metric | Value
Total tasks | 1100
Stable production task | TASK-1100
Image registry slots | 140
Phase | Tasks | P0 | Launch gates | Status | Outcome
P01 — Governance and repository control | 50 |  |  | In progress | Dependency-ready accepted phase
P02 — Business, legal and pilot evidence | 50 |  |  |  | Dependency-ready accepted phase
P03 — Architecture and platform foundation | 50 |  |  |  | Dependency-ready accepted phase
P04 — World-class design and dynamic experience | 75 |  |  |  | Dependency-ready accepted phase
P05 — Identity and access control | 50 |  |  |  | Dependency-ready accepted phase
P06 — Location, maps and property catalogue | 75 |  |  |  | Dependency-ready accepted phase
P07 — Media and 140-image production pipeline | 75 |  |  |  | Dependency-ready accepted phase
P08 — Seller reservation and listing workflow | 75 |  |  |  | Dependency-ready accepted phase
P09 — Operations and administration | 75 |  |  |  | Dependency-ready accepted phase
P10 — Buyer marketplace experience | 75 |  |  |  | Dependency-ready accepted phase
P11 — Pricing, listing and inventory state | 50 |  |  |  | Dependency-ready accepted phase
P12 — Checkout, payments and ledger | 75 |  |  |  | Dependency-ready accepted phase
P13 — Transfer, Passport and arrival | 50 |  |  |  | Dependency-ready accepted phase
P14 — Claims, recovery and seller payout | 50 |  |  |  | Dependency-ready accepted phase
P15 — CRM, notifications and responsible intelligence | 40 |  |  |  | Dependency-ready accepted phase
P16 — Security, privacy, accessibility and reliability | 40 |  |  |  | Dependency-ready accepted phase
P17 — Full-system QA and launch rehearsal | 30 |  |  |  | Dependency-ready accepted phase
P18 — Production launch and monitored operations | 15 |  |  |  | Public production launch
P19 — Final design, page and production certification | 100 |  |  |  | Dependency-ready accepted phase
Production definition | Requirement | Owner | Evidence | Gate | Notes
Real public website | Approved domain serves the production release | Founder / Release Manager |  | Required | Not a mock or disconnected preview
Complete product | Buyer, seller and private operations workflows are connected | Product / Engineering |  | Required | Server-authoritative state
Destination visual engine | Confirmed destination changes approved imagery and context across relevant pages | Design / Location Platform |  | Required | Stable transactional layout
Commercial safety | Payments, ledger, claims, refunds and payouts use approved providers and controls | Finance / Compliance |  | Required | No unsupported production money flow
Operability | Monitoring, support, emergency pause, backup and rollback are active | Operations / SRE |  | Required | First live journey reconciled

## Tasks
Exact 1,100-task execution ledger
Update Status, Evidence Link and PR / Commit as work progresses. Do not mark Done without acceptance evidence.
Task ID | Phase | Workstream | Title | Objective | Deliverable | Acceptance Criteria | Depends On | Owner | Priority | Environment | Launch Gate | Status | Evidence Link | PR / Commit | Notes
TASK-0001 | P01 — Governance and repository control | Project control and source governance | Establish the governing charter — Project control and source governance | Establish the governing charter for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: approved charter | Authority, scope, exclusions and production boundaries are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. |  | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/GOVERNING-CHARTER.md; docs/ai/TASK-0001-GOVERNING-CHARTER.md | fcdfb4a76c73fade8eeb39588979113d37ae6ca2 | Verified 2026-10-10: charter acceptance mapping and disclosed external blockers; GitHub API Forbidden, PR pending.
TASK-0002 | P01 — Governance and repository control | Project control and source governance | Map canonical sources — Project control and source governance | Map canonical sources for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: source hierarchy | Current audited sources outrank drafts and duplicates. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0001 | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/SOURCE-HIERARCHY.md; docs/ai/TASK-0002-CANONICAL-SOURCES.md | c737348a496b911362ff32cf51dfb30413ac4bb5 | Verified 2026-10-10: precedence, server/provider truth, historical evidence and explicit source gaps mapped.
TASK-0003 | P01 — Governance and repository control | Project control and source governance | Assign accountable owners — Project control and source governance | Assign accountable owners for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: ownership matrix | Every decision and artifact has one accountable owner. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0002 | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/OWNERSHIP-MATRIX.md; docs/ai/TASK-0003-ACCOUNTABLE-OWNERS.md | 8550fa85d412d0aac27ee1d32256eb28d7a6b819 | Verified 2026-10-10: every artifact class has one accountable role; unevidenced human names remain Unassigned.
TASK-0004 | P01 — Governance and repository control | Project control and source governance | Define decision rights — Project control and source governance | Define decision rights for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: decision-rights register | Approval, consultation and escalation responsibilities are clear. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0003 | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/DECISION-RIGHTS.md; docs/ai/TASK-0004-DECISION-RIGHTS.md | 5d8fd36ca5fb19fdb3f8088f31d6c12e7a9b9a22 | Verified 2026-10-10: approval, consultation, blocking, escalation and emergency rights mapped without inventing human authority.
TASK-0005 | P01 — Governance and repository control | Project control and source governance | Inventory existing artifacts — Project control and source governance | Inventory existing artifacts for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: artifact inventory | Repositories, branches, deployments, workbooks and provider projects are identified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0004 | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/ARTIFACT-INVENTORY.md; docs/ai/TASK-0005-ARTIFACT-INVENTORY.md | 929113eb9c500d4ef161708684cdd2e00013f1bd | Verified 2026-10-10: repository, 33 origin task branches, PR refs 1-5, hosting configuration, workbook versions and provider-project gaps inventoried; GitHub API and external deployments/providers remain unverified.
TASK-0006 | P01 — Governance and repository control | Project control and source governance | Reconcile duplicates and stale copies — Project control and source governance | Reconcile duplicates and stale copies for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: reconciliation record | The canonical item and retained history are documented without data loss. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0005 | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/ARTIFACT-RECONCILIATION.md; docs/ai/TASK-0006-ARTIFACT-RECONCILIATION.md | 7c6ab63ae0c13a140b330c23a7e14c60cf796796 | Verified 2026-10-10: canonical and retained workbooks, roadmaps, branches, PR refs, deployment configurations, provider proposals and linked sources reconciled without deletion or unsupported promotion.
TASK-0007 | P01 — Governance and repository control | Project control and source governance | Baseline the live state — Project control and source governance | Baseline the live state for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: verifiable baseline | URLs, commits, versions, tests and environment status are captured. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0006 | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/LIVE-STATE-BASELINE.md; docs/ai/TASK-0007-LIVE-STATE-BASELINE.md | bee6ac94f01c584e58395445f1a2ee606cf62da3 | Verified 2026-10-10: commits, versions, tests, local URLs and environment boundaries captured; local customer/operations/API contracts pass while preview, provider and production state remain unverified.
TASK-0008 | P01 — Governance and repository control | Project control and source governance | Map the roadmap and task IDs — Project control and source governance | Map the roadmap and task IDs for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: roadmap crosswalk | Existing tasks and this workstream map without conflicting IDs. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0007 | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/ROADMAP-CROSSWALK.md; docs/ai/TASK-0008-ROADMAP-CROSSWALK.md | 0c7c869821a33ae615262bbccf1af7c183eaaf5a | Verified 2026-10-10: all 19 current phases and exact task ranges mapped; retained earlier-roadmap branches classified as historical evidence requiring current-row revalidation.
TASK-0009 | P01 — Governance and repository control | Project control and source governance | Define completion evidence — Project control and source governance | Define completion evidence for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: evidence checklist | A task cannot close from narrative alone. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0008 | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/COMPLETION-EVIDENCE-CHECKLIST.md; docs/ai/TASK-0009-COMPLETION-EVIDENCE.md | 8d30f0f7e3ec5bf587288ecf6ac9c69a8fd5f02a | Verified 2026-10-10: universal/task-class evidence, real command policy, fail-closed proof and completion decisions defined; typecheck, builds and 9 unit tests pass.
TASK-0010 | P01 — Governance and repository control | Project control and source governance | Create the risk register — Project control and source governance | Create the risk register for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: risk register | Severity, likelihood, owner, mitigation and gate are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0009 | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/RISK-REGISTER.md; docs/ai/TASK-0010-RISK-REGISTER.md | afd5d24ac87cb90418ede91227e8bf75212b83e7 | Verified 2026-10-10: 19 current risks record severity, likelihood, accountable role, mitigation evidence and affected gate; none closed without authoritative proof.
TASK-0011 | P01 — Governance and repository control | Project control and source governance | Map dependencies and critical path — Project control and source governance | Map dependencies and critical path for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: dependency graph | Blocking and parallel work are distinguishable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0010 | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/DEPENDENCY-CRITICAL-PATH.md; docs/ai/TASK-0011-DEPENDENCY-CRITICAL-PATH.md | 985f272916f5c7793416912bed72ecad681df9ba | Verified 2026-10-10: 1,100 nodes and 1,122 resolved edges form an acyclic graph; ready set, parallel streams, convergence gates and 537-task structural longest chain recorded; production/deployment gates remain separate.
TASK-0012 | P01 — Governance and repository control | Project control and source governance | Define branch and environment policy — Project control and source governance | Define branch and environment policy for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: branch and environment standard | Preview, staging and production boundaries are enforced. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0011 | Technical Program Lead | P1 | Planning / evidence | No | Done | docs/project-control/BRANCH-ENVIRONMENT-POLICY.md; docs/ai/TASK-0012-BRANCH-ENVIRONMENT-POLICY.md | a8c6a8d745d3f439e9ab525afa5660f3b8241599 | Verified 2026-10-10: task, review, integration, preview, staging and production boundaries defined with fail-closed promotion evidence; hosted enforcement remains blocked by unverified Vercel identity/link and unavailable GitHub API review/CI evidence.
TASK-0013 | P01 — Governance and repository control | Project control and source governance | Define change control — Project control and source governance | Define change control for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: change-control procedure | High-risk and production changes have explicit approval paths. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0012 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0014 | P01 — Governance and repository control | Project control and source governance | Create working templates — Project control and source governance | Create working templates for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: task, ADR, incident and handoff templates | Templates capture source, invariant, tests and continuation state. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0013 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0015 | P01 — Governance and repository control | Project control and source governance | Implement the control register — Project control and source governance | Implement the control register for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: maintained control register | Status, evidence, owner and next action are queryable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0014 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0016 | P01 — Governance and repository control | Project control and source governance | Link repository and external evidence — Project control and source governance | Link repository and external evidence for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: traceable evidence links | Every completed item points to durable source evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0015 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0017 | P01 — Governance and repository control | Project control and source governance | Record open questions — Project control and source governance | Record open questions for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: open-question register | Uncertainty is visible and never converted into an unsupported fact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0016 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0018 | P01 — Governance and repository control | Project control and source governance | Review data and security governance — Project control and source governance | Review data and security governance for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: governance review | Sensitive data and privileged actions have defined controls. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0017 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0019 | P01 — Governance and repository control | Project control and source governance | Validate access and segregation — Project control and source governance | Validate access and segregation for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: access review | Least privilege and separation of duties are evidenced. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0018 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0020 | P01 — Governance and repository control | Project control and source governance | Test end-to-end traceability — Project control and source governance | Test end-to-end traceability for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: traceability test | A requirement can be followed through code, test, deployment and operation. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0019 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0021 | P01 — Governance and repository control | Project control and source governance | Test recovery and rollback — Project control and source governance | Test recovery and rollback for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: recovery evidence | The team can restore prior safe state without deleting unique work. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0020 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0022 | P01 — Governance and repository control | Project control and source governance | Conduct multidisciplinary review — Project control and source governance | Conduct multidisciplinary review for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: review record | Product, design, engineering and operations concerns are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0021 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0023 | P01 — Governance and repository control | Project control and source governance | Resolve critical governance gaps — Project control and source governance | Resolve critical governance gaps for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: resolved P0/P1 gap list | No unresolved critical control blocks downstream execution. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0022 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0024 | P01 — Governance and repository control | Project control and source governance | Publish the governance runbook — Project control and source governance | Publish the governance runbook for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: governance runbook | A new team member can continue without conversation history. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0023 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0025 | P01 — Governance and repository control | Project control and source governance | Pass the governance gate — Project control and source governance | Pass the governance gate for Project control and source governance. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Project control and source governance: approved phase gate | Canonical state, owners, evidence and next dependencies are accepted. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0024 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0026 | P01 — Governance and repository control | Repository and deployment baseline | Establish the governing charter — Repository and deployment baseline | Establish the governing charter for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: approved charter | Authority, scope, exclusions and production boundaries are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. |  | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0027 | P01 — Governance and repository control | Repository and deployment baseline | Map canonical sources — Repository and deployment baseline | Map canonical sources for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: source hierarchy | Current audited sources outrank drafts and duplicates. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0026 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0028 | P01 — Governance and repository control | Repository and deployment baseline | Assign accountable owners — Repository and deployment baseline | Assign accountable owners for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: ownership matrix | Every decision and artifact has one accountable owner. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0027 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0029 | P01 — Governance and repository control | Repository and deployment baseline | Define decision rights — Repository and deployment baseline | Define decision rights for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: decision-rights register | Approval, consultation and escalation responsibilities are clear. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0028 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0030 | P01 — Governance and repository control | Repository and deployment baseline | Inventory existing artifacts — Repository and deployment baseline | Inventory existing artifacts for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: artifact inventory | Repositories, branches, deployments, workbooks and provider projects are identified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0029 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0031 | P01 — Governance and repository control | Repository and deployment baseline | Reconcile duplicates and stale copies — Repository and deployment baseline | Reconcile duplicates and stale copies for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: reconciliation record | The canonical item and retained history are documented without data loss. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0030 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0032 | P01 — Governance and repository control | Repository and deployment baseline | Baseline the live state — Repository and deployment baseline | Baseline the live state for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: verifiable baseline | URLs, commits, versions, tests and environment status are captured. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0031 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0033 | P01 — Governance and repository control | Repository and deployment baseline | Map the roadmap and task IDs — Repository and deployment baseline | Map the roadmap and task IDs for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: roadmap crosswalk | Existing tasks and this workstream map without conflicting IDs. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0032 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0034 | P01 — Governance and repository control | Repository and deployment baseline | Define completion evidence — Repository and deployment baseline | Define completion evidence for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: evidence checklist | A task cannot close from narrative alone. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0033 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0035 | P01 — Governance and repository control | Repository and deployment baseline | Create the risk register — Repository and deployment baseline | Create the risk register for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: risk register | Severity, likelihood, owner, mitigation and gate are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0034 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0036 | P01 — Governance and repository control | Repository and deployment baseline | Map dependencies and critical path — Repository and deployment baseline | Map dependencies and critical path for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: dependency graph | Blocking and parallel work are distinguishable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0035 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0037 | P01 — Governance and repository control | Repository and deployment baseline | Define branch and environment policy — Repository and deployment baseline | Define branch and environment policy for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: branch and environment standard | Preview, staging and production boundaries are enforced. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0036 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0038 | P01 — Governance and repository control | Repository and deployment baseline | Define change control — Repository and deployment baseline | Define change control for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: change-control procedure | High-risk and production changes have explicit approval paths. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0037 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0039 | P01 — Governance and repository control | Repository and deployment baseline | Create working templates — Repository and deployment baseline | Create working templates for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: task, ADR, incident and handoff templates | Templates capture source, invariant, tests and continuation state. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0038 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0040 | P01 — Governance and repository control | Repository and deployment baseline | Implement the control register — Repository and deployment baseline | Implement the control register for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: maintained control register | Status, evidence, owner and next action are queryable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0039 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0041 | P01 — Governance and repository control | Repository and deployment baseline | Link repository and external evidence — Repository and deployment baseline | Link repository and external evidence for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: traceable evidence links | Every completed item points to durable source evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0040 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0042 | P01 — Governance and repository control | Repository and deployment baseline | Record open questions — Repository and deployment baseline | Record open questions for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: open-question register | Uncertainty is visible and never converted into an unsupported fact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0041 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0043 | P01 — Governance and repository control | Repository and deployment baseline | Review data and security governance — Repository and deployment baseline | Review data and security governance for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: governance review | Sensitive data and privileged actions have defined controls. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0042 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0044 | P01 — Governance and repository control | Repository and deployment baseline | Validate access and segregation — Repository and deployment baseline | Validate access and segregation for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: access review | Least privilege and separation of duties are evidenced. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0043 | Technical Program Lead | P1 | Planning / evidence | No | Not started
TASK-0045 | P01 — Governance and repository control | Repository and deployment baseline | Test end-to-end traceability — Repository and deployment baseline | Test end-to-end traceability for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: traceability test | A requirement can be followed through code, test, deployment and operation. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0044 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0046 | P01 — Governance and repository control | Repository and deployment baseline | Test recovery and rollback — Repository and deployment baseline | Test recovery and rollback for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: recovery evidence | The team can restore prior safe state without deleting unique work. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0045 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0047 | P01 — Governance and repository control | Repository and deployment baseline | Conduct multidisciplinary review — Repository and deployment baseline | Conduct multidisciplinary review for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: review record | Product, design, engineering and operations concerns are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0046 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0048 | P01 — Governance and repository control | Repository and deployment baseline | Resolve critical governance gaps — Repository and deployment baseline | Resolve critical governance gaps for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: resolved P0/P1 gap list | No unresolved critical control blocks downstream execution. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0047 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0049 | P01 — Governance and repository control | Repository and deployment baseline | Publish the governance runbook — Repository and deployment baseline | Publish the governance runbook for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: governance runbook | A new team member can continue without conversation history. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0048 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0050 | P01 — Governance and repository control | Repository and deployment baseline | Pass the governance gate — Repository and deployment baseline | Pass the governance gate for Repository and deployment baseline. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Repository and deployment baseline: approved phase gate | Canonical state, owners, evidence and next dependencies are accepted. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0049, TASK-0025 | Technical Program Lead | P0 | Planning / evidence | Yes | Not started
TASK-0051 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Define the exact evidence question — Reservation transfer policy and customer protection | Define the exact evidence question for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: bounded evidence question | The booking, policy, jurisdiction and decision affected are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0050 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0052 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Identify primary authoritative sources — Reservation transfer policy and customer protection | Identify primary authoritative sources for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: primary-source map | Official documents are separated from commentary and assumptions. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0051 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0053 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Record jurisdiction and applicability — Reservation transfer policy and customer protection | Record jurisdiction and applicability for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: applicability record | Territory, customer, seller and transaction scope are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0052 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0054 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Capture current terms and versions — Reservation transfer policy and customer protection | Capture current terms and versions for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: versioned terms record | Retrieval date, URL, version and material clauses are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0053 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0055 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Collect supporting evidence — Reservation transfer policy and customer protection | Collect supporting evidence for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: evidence bundle | Evidence is authentic, minimal, private and linked to the question. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0054 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0056 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Validate source freshness — Reservation transfer policy and customer protection | Validate source freshness for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: freshness assessment | Stale or undated evidence cannot silently pass a gate. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0055 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0057 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Reconcile contradictions — Reservation transfer policy and customer protection | Reconcile contradictions for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: conflict analysis | Conflicting sources remain visible with a resolution owner. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0056 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0058 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Determine exact reservation impact — Reservation transfer policy and customer protection | Determine exact reservation impact for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: reservation-level finding | No brand-wide or property-wide inference replaces exact booking analysis. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0057 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0059 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Define seller obligations — Reservation transfer policy and customer protection | Define seller obligations for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: seller obligation specification | Truth, update, cooperation and cancellation duties are clear. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0058 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0060 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Define buyer rights and limitations — Reservation transfer policy and customer protection | Define buyer rights and limitations for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: buyer protection specification | Promised outcomes and exclusions are supportable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0059 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0061 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Review consumer-law implications — Reservation transfer policy and customer protection | Review consumer-law implications for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: consumer-law issue record | Required disclosures and prohibited claims are identified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0060 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0062 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Review tax and invoicing implications — Reservation transfer policy and customer protection | Review tax and invoicing implications for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: tax and invoicing issue record | Unapproved tax treatment stays gated. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0061 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0063 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Review payment and settlement implications — Reservation transfer policy and customer protection | Review payment and settlement implications for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: payment feasibility record | Provider, KYC, marketplace and refund requirements are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0062 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0064 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Review reserve and protection requirements — Reservation transfer policy and customer protection | Review reserve and protection requirements for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: capital and protection record | Risk capacity is separate from reservation eligibility. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0063 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0065 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Verify property and channel cooperation — Reservation transfer policy and customer protection | Verify property and channel cooperation for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: cooperation evidence | No hotel, OTA or source approval is claimed without evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0064 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0066 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Select the controlled pilot boundary — Reservation transfer policy and customer protection | Select the controlled pilot boundary for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: pilot boundary decision | City, dates, events, properties and transaction caps are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0065 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0067 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Define property admission criteria — Reservation transfer policy and customer protection | Define property admission criteria for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: property admission standard | Only properties meeting evidence and operational standards enter the pilot. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0066 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0068 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Verify provider capabilities — Reservation transfer policy and customer protection | Verify provider capabilities for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: provider capability matrix | Capabilities, limits, regions, costs and blockers use current evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0067 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0069 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Assess operational and correlated risk — Reservation transfer policy and customer protection | Assess operational and correlated risk for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: risk assessment | Failure modes, concentration and manual capacity are quantified where possible. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0068 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0070 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Record the decision and rationale — Reservation transfer policy and customer protection | Record the decision and rationale for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: decision record | Decision, alternatives, evidence and expiry are auditable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0069 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0071 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Obtain legal review evidence — Reservation transfer policy and customer protection | Obtain legal review evidence for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: legal review gate | Open legal issues are assigned and gated rather than assumed away. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0070 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0072 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Obtain finance and tax review evidence — Reservation transfer policy and customer protection | Obtain finance and tax review evidence for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: finance review gate | Money flows, invoices, reserves and reconciliation are approved or blocked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0071 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0073 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Obtain operations review evidence — Reservation transfer policy and customer protection | Obtain operations review evidence for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: operations review gate | The team can execute the policy with documented capacity. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0072 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0074 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Bind unresolved issues to feature flags — Reservation transfer policy and customer protection | Bind unresolved issues to feature flags for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: feature-gate mapping | Unsafe capability remains disabled until its evidence gate passes. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0073 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0075 | P02 — Business, legal and pilot evidence | Reservation transfer policy and customer protection | Pass the pilot-readiness evidence gate — Reservation transfer policy and customer protection | Pass the pilot-readiness evidence gate for Reservation transfer policy and customer protection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation transfer policy and customer protection: accepted evidence pack | All required evidence is current, attributable and linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0074 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0076 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Define the exact evidence question — Pilot, provider and commercial readiness | Define the exact evidence question for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: bounded evidence question | The booking, policy, jurisdiction and decision affected are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0050 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0077 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Identify primary authoritative sources — Pilot, provider and commercial readiness | Identify primary authoritative sources for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: primary-source map | Official documents are separated from commentary and assumptions. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0076 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0078 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Record jurisdiction and applicability — Pilot, provider and commercial readiness | Record jurisdiction and applicability for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: applicability record | Territory, customer, seller and transaction scope are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0077 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0079 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Capture current terms and versions — Pilot, provider and commercial readiness | Capture current terms and versions for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: versioned terms record | Retrieval date, URL, version and material clauses are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0078 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0080 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Collect supporting evidence — Pilot, provider and commercial readiness | Collect supporting evidence for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: evidence bundle | Evidence is authentic, minimal, private and linked to the question. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0079 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0081 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Validate source freshness — Pilot, provider and commercial readiness | Validate source freshness for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: freshness assessment | Stale or undated evidence cannot silently pass a gate. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0080 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0082 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Reconcile contradictions — Pilot, provider and commercial readiness | Reconcile contradictions for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: conflict analysis | Conflicting sources remain visible with a resolution owner. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0081 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0083 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Determine exact reservation impact — Pilot, provider and commercial readiness | Determine exact reservation impact for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: reservation-level finding | No brand-wide or property-wide inference replaces exact booking analysis. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0082 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0084 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Define seller obligations — Pilot, provider and commercial readiness | Define seller obligations for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: seller obligation specification | Truth, update, cooperation and cancellation duties are clear. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0083 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0085 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Define buyer rights and limitations — Pilot, provider and commercial readiness | Define buyer rights and limitations for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: buyer protection specification | Promised outcomes and exclusions are supportable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0084 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0086 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Review consumer-law implications — Pilot, provider and commercial readiness | Review consumer-law implications for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: consumer-law issue record | Required disclosures and prohibited claims are identified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0085 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0087 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Review tax and invoicing implications — Pilot, provider and commercial readiness | Review tax and invoicing implications for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: tax and invoicing issue record | Unapproved tax treatment stays gated. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0086 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0088 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Review payment and settlement implications — Pilot, provider and commercial readiness | Review payment and settlement implications for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: payment feasibility record | Provider, KYC, marketplace and refund requirements are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0087 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0089 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Review reserve and protection requirements — Pilot, provider and commercial readiness | Review reserve and protection requirements for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: capital and protection record | Risk capacity is separate from reservation eligibility. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0088 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0090 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Verify property and channel cooperation — Pilot, provider and commercial readiness | Verify property and channel cooperation for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: cooperation evidence | No hotel, OTA or source approval is claimed without evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0089 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0091 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Select the controlled pilot boundary — Pilot, provider and commercial readiness | Select the controlled pilot boundary for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: pilot boundary decision | City, dates, events, properties and transaction caps are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0090 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0092 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Define property admission criteria — Pilot, provider and commercial readiness | Define property admission criteria for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: property admission standard | Only properties meeting evidence and operational standards enter the pilot. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0091 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0093 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Verify provider capabilities — Pilot, provider and commercial readiness | Verify provider capabilities for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: provider capability matrix | Capabilities, limits, regions, costs and blockers use current evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0092 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0094 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Assess operational and correlated risk — Pilot, provider and commercial readiness | Assess operational and correlated risk for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: risk assessment | Failure modes, concentration and manual capacity are quantified where possible. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0093 | Founder and Compliance Lead | P1 | Planning / evidence | No | Not started
TASK-0095 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Record the decision and rationale — Pilot, provider and commercial readiness | Record the decision and rationale for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: decision record | Decision, alternatives, evidence and expiry are auditable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0094 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0096 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Obtain legal review evidence — Pilot, provider and commercial readiness | Obtain legal review evidence for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: legal review gate | Open legal issues are assigned and gated rather than assumed away. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0095 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0097 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Obtain finance and tax review evidence — Pilot, provider and commercial readiness | Obtain finance and tax review evidence for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: finance review gate | Money flows, invoices, reserves and reconciliation are approved or blocked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0096 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0098 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Obtain operations review evidence — Pilot, provider and commercial readiness | Obtain operations review evidence for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: operations review gate | The team can execute the policy with documented capacity. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0097 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0099 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Bind unresolved issues to feature flags — Pilot, provider and commercial readiness | Bind unresolved issues to feature flags for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: feature-gate mapping | Unsafe capability remains disabled until its evidence gate passes. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0098 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0100 | P02 — Business, legal and pilot evidence | Pilot, provider and commercial readiness | Pass the pilot-readiness evidence gate — Pilot, provider and commercial readiness | Pass the pilot-readiness evidence gate for Pilot, provider and commercial readiness. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pilot, provider and commercial readiness: accepted evidence pack | All required evidence is current, attributable and linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0099, TASK-0075 | Founder and Compliance Lead | P0 | Planning / evidence | Yes | Not started
TASK-0101 | P03 — Architecture and platform foundation | Application architecture and toolchain | Define outcome and acceptance — Application architecture and toolchain | Define outcome and acceptance for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0100 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0102 | P03 — Architecture and platform foundation | Application architecture and toolchain | Trace controlling requirements — Application architecture and toolchain | Trace controlling requirements for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0101 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0103 | P03 — Architecture and platform foundation | Application architecture and toolchain | Audit the current implementation — Application architecture and toolchain | Audit the current implementation for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0102 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0104 | P03 — Architecture and platform foundation | Application architecture and toolchain | Write user stories and edge cases — Application architecture and toolchain | Write user stories and edge cases for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0103 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0105 | P03 — Architecture and platform foundation | Application architecture and toolchain | Model roles and permissions — Application architecture and toolchain | Model roles and permissions for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0104 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0106 | P03 — Architecture and platform foundation | Application architecture and toolchain | Design the data contract — Application architecture and toolchain | Design the data contract for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0105 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0107 | P03 — Architecture and platform foundation | Application architecture and toolchain | Define the state machine — Application architecture and toolchain | Define the state machine for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0106 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0108 | P03 — Architecture and platform foundation | Application architecture and toolchain | Define commands, queries and events — Application architecture and toolchain | Define commands, queries and events for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0107 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0109 | P03 — Architecture and platform foundation | Application architecture and toolchain | Map the complete UX flow — Application architecture and toolchain | Map the complete UX flow for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0108 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0110 | P03 — Architecture and platform foundation | Application architecture and toolchain | Create responsive wireframes — Application architecture and toolchain | Create responsive wireframes for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0109 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0111 | P03 — Architecture and platform foundation | Application architecture and toolchain | Complete high-fidelity design — Application architecture and toolchain | Complete high-fidelity design for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0110 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0112 | P03 — Architecture and platform foundation | Application architecture and toolchain | Specify accessibility behaviour — Application architecture and toolchain | Specify accessibility behaviour for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0111 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0113 | P03 — Architecture and platform foundation | Application architecture and toolchain | Implement schema and migrations — Application architecture and toolchain | Implement schema and migrations for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0112 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0114 | P03 — Architecture and platform foundation | Application architecture and toolchain | Implement server-side domain logic — Application architecture and toolchain | Implement server-side domain logic for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0113 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0115 | P03 — Architecture and platform foundation | Application architecture and toolchain | Implement the frontend foundation — Application architecture and toolchain | Implement the frontend foundation for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0114 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0116 | P03 — Architecture and platform foundation | Application architecture and toolchain | Implement the happy path — Application architecture and toolchain | Implement the happy path for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0115 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0117 | P03 — Architecture and platform foundation | Application architecture and toolchain | Implement non-happy states — Application architecture and toolchain | Implement non-happy states for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0116 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0118 | P03 — Architecture and platform foundation | Application architecture and toolchain | Add audit and observability — Application architecture and toolchain | Add audit and observability for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0117 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0119 | P03 — Architecture and platform foundation | Application architecture and toolchain | Apply security and privacy controls — Application architecture and toolchain | Apply security and privacy controls for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0118 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0120 | P03 — Architecture and platform foundation | Application architecture and toolchain | Write unit tests — Application architecture and toolchain | Write unit tests for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0119 | Principal Engineer | P0 | Development / preview | Yes | Not started
TASK-0121 | P03 — Architecture and platform foundation | Application architecture and toolchain | Write integration tests — Application architecture and toolchain | Write integration tests for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0120 | Principal Engineer | P0 | Development / preview | Yes | Not started
TASK-0122 | P03 — Architecture and platform foundation | Application architecture and toolchain | Write end-to-end tests — Application architecture and toolchain | Write end-to-end tests for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0121 | Principal Engineer | P0 | Development / preview | Yes | Not started
TASK-0123 | P03 — Architecture and platform foundation | Application architecture and toolchain | Validate performance and resilience — Application architecture and toolchain | Validate performance and resilience for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0122 | Principal Engineer | P0 | Development / preview | Yes | Not started
TASK-0124 | P03 — Architecture and platform foundation | Application architecture and toolchain | Publish operating documentation — Application architecture and toolchain | Publish operating documentation for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0123 | Principal Engineer | P0 | Development / preview | Yes | Not started
TASK-0125 | P03 — Architecture and platform foundation | Application architecture and toolchain | Pass preview acceptance — Application architecture and toolchain | Pass preview acceptance for Application architecture and toolchain. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Application architecture and toolchain: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0124 | Principal Engineer | P0 | Preview gate | Yes | Not started
TASK-0126 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Define outcome and acceptance — Environments, CI/CD and observability foundation | Define outcome and acceptance for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0100 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0127 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Trace controlling requirements — Environments, CI/CD and observability foundation | Trace controlling requirements for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0126 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0128 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Audit the current implementation — Environments, CI/CD and observability foundation | Audit the current implementation for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0127 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0129 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Write user stories and edge cases — Environments, CI/CD and observability foundation | Write user stories and edge cases for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0128 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0130 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Model roles and permissions — Environments, CI/CD and observability foundation | Model roles and permissions for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0129 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0131 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Design the data contract — Environments, CI/CD and observability foundation | Design the data contract for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0130 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0132 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Define the state machine — Environments, CI/CD and observability foundation | Define the state machine for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0131 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0133 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Define commands, queries and events — Environments, CI/CD and observability foundation | Define commands, queries and events for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0132 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0134 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Map the complete UX flow — Environments, CI/CD and observability foundation | Map the complete UX flow for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0133 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0135 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Create responsive wireframes — Environments, CI/CD and observability foundation | Create responsive wireframes for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0134 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0136 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Complete high-fidelity design — Environments, CI/CD and observability foundation | Complete high-fidelity design for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0135 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0137 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Specify accessibility behaviour — Environments, CI/CD and observability foundation | Specify accessibility behaviour for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0136 | Principal Engineer | P1 | Local / design | No | Not started
TASK-0138 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Implement schema and migrations — Environments, CI/CD and observability foundation | Implement schema and migrations for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0137 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0139 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Implement server-side domain logic — Environments, CI/CD and observability foundation | Implement server-side domain logic for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0138 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0140 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Implement the frontend foundation — Environments, CI/CD and observability foundation | Implement the frontend foundation for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0139 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0141 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Implement the happy path — Environments, CI/CD and observability foundation | Implement the happy path for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0140 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0142 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Implement non-happy states — Environments, CI/CD and observability foundation | Implement non-happy states for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0141 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0143 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Add audit and observability — Environments, CI/CD and observability foundation | Add audit and observability for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0142 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0144 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Apply security and privacy controls — Environments, CI/CD and observability foundation | Apply security and privacy controls for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0143 | Principal Engineer | P1 | Development / preview | No | Not started
TASK-0145 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Write unit tests — Environments, CI/CD and observability foundation | Write unit tests for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0144 | Principal Engineer | P0 | Development / preview | Yes | Not started
TASK-0146 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Write integration tests — Environments, CI/CD and observability foundation | Write integration tests for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0145 | Principal Engineer | P0 | Development / preview | Yes | Not started
TASK-0147 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Write end-to-end tests — Environments, CI/CD and observability foundation | Write end-to-end tests for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0146 | Principal Engineer | P0 | Development / preview | Yes | Not started
TASK-0148 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Validate performance and resilience — Environments, CI/CD and observability foundation | Validate performance and resilience for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0147 | Principal Engineer | P0 | Development / preview | Yes | Not started
TASK-0149 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Publish operating documentation — Environments, CI/CD and observability foundation | Publish operating documentation for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0148 | Principal Engineer | P0 | Development / preview | Yes | Not started
TASK-0150 | P03 — Architecture and platform foundation | Environments, CI/CD and observability foundation | Pass preview acceptance — Environments, CI/CD and observability foundation | Pass preview acceptance for Environments, CI/CD and observability foundation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Environments, CI/CD and observability foundation: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0149, TASK-0125 | Principal Engineer | P0 | Preview gate | Yes | Not started
TASK-0151 | P04 — World-class design and dynamic experience | Global design system | Define experience goals and users — Global design system | Define experience goals and users for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: experience brief | Buyer, seller and operations outcomes are measurable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0150 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0152 | P04 — World-class design and dynamic experience | Global design system | Map jobs and complete journeys — Global design system | Map jobs and complete journeys for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: journey map | Entry, decision, transaction and support moments are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0151 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0153 | P04 — World-class design and dynamic experience | Global design system | Audit current screens — Global design system | Audit current screens for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: screen-level gap audit | Confusion, missing states and misleading affordances are evidenced. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0152 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0154 | P04 — World-class design and dynamic experience | Global design system | Design information architecture — Global design system | Design information architecture for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: route and navigation model | Public, buyer, seller and operations navigation are separated. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0153 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0155 | P04 — World-class design and dynamic experience | Global design system | Write content hierarchy and copy — Global design system | Write content hierarchy and copy for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: content specification | The core transfer idea is understandable without insider terminology. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0154 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0156 | P04 — World-class design and dynamic experience | Global design system | Define interaction principles — Global design system | Define interaction principles for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: interaction contract | Progressive disclosure, confirmation and recovery are consistent. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0155 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0157 | P04 — World-class design and dynamic experience | Global design system | Map data and state to UI — Global design system | Map data and state to UI for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: UI state matrix | Every visual status maps to server-confirmed data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0156 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0158 | P04 — World-class design and dynamic experience | Global design system | Define layout system — Global design system | Define layout system for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: grid and spatial system | Content density, maximum widths and reading order are consistent. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0157 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0159 | P04 — World-class design and dynamic experience | Global design system | Define responsive behavior — Global design system | Define responsive behavior for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: breakpoint behavior | Mobile, tablet, desktop and ultra-wide layouts preserve task completion. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0158 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0160 | P04 — World-class design and dynamic experience | Global design system | Create low-fidelity wireframes — Global design system | Create low-fidelity wireframes for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: wireframe set | Critical flows and alternatives can be reviewed before visual polish. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0159 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0161 | P04 — World-class design and dynamic experience | Global design system | Specify reusable components — Global design system | Specify reusable components for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: component inventory | States, variants and ownership prevent one-off UI drift. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0160 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0162 | P04 — World-class design and dynamic experience | Global design system | Define visual mood and tokens — Global design system | Define visual mood and tokens for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: visual token set | Colour, typography, radius, shadow, image and motion choices are coherent. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0161 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0163 | P04 — World-class design and dynamic experience | Global design system | Create high-fidelity designs — Global design system | Create high-fidelity designs for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: high-fidelity screen set | Realistic content and complete states establish the quality bar. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0162 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0164 | P04 — World-class design and dynamic experience | Global design system | Build an interactive prototype — Global design system | Build an interactive prototype for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: reviewable prototype | Primary journeys, transitions and destination changes can be tested. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0163 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0165 | P04 — World-class design and dynamic experience | Global design system | Complete accessibility review — Global design system | Complete accessibility review for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: accessibility annotations | Keyboard, focus, semantics, errors, contrast and motion are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0164 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0166 | P04 — World-class design and dynamic experience | Global design system | Implement design tokens — Global design system | Implement design tokens for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: code-native design tokens | Tokens are typed, documented and usable across all workspaces. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0165 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0167 | P04 — World-class design and dynamic experience | Global design system | Implement responsive components — Global design system | Implement responsive components for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: shared component implementation | Components match approved states without page-specific forks. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0166 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0168 | P04 — World-class design and dynamic experience | Global design system | Implement non-happy visual states — Global design system | Implement non-happy visual states for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: complete state implementation | Loading, empty, stale, error and permission states are intentional. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0167 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0169 | P04 — World-class design and dynamic experience | Global design system | Implement restrained motion — Global design system | Implement restrained motion for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: motion system | Motion clarifies change and respects reduced-motion settings. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0168 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0170 | P04 — World-class design and dynamic experience | Global design system | Write component tests — Global design system | Write component tests for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: component test suite | Variants, keyboard behavior and state rendering are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0169 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0171 | P04 — World-class design and dynamic experience | Global design system | Create visual regression coverage — Global design system | Create visual regression coverage for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: visual baseline | Critical breakpoints and themes detect unintended drift. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0170 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0172 | P04 — World-class design and dynamic experience | Global design system | Run usability testing — Global design system | Run usability testing for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: usability findings | Representative users can complete the flow and understand status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0171 | Product Design Lead | P0 | Development / preview | Yes | Not started
TASK-0173 | P04 — World-class design and dynamic experience | Global design system | Validate experience performance — Global design system | Validate experience performance for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: UX performance report | Images, transitions and hydration meet interaction budgets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0172 | Product Design Lead | P0 | Development / preview | Yes | Not started
TASK-0174 | P04 — World-class design and dynamic experience | Global design system | Publish design documentation — Global design system | Publish design documentation for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: design system documentation | Design and engineering share one current source. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0173 | Product Design Lead | P0 | Development / preview | Yes | Not started
TASK-0175 | P04 — World-class design and dynamic experience | Global design system | Pass design acceptance — Global design system | Pass design acceptance for Global design system. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Global design system: accepted experience evidence | Product, design, accessibility and engineering approve the preview. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0174 | Product Design Lead | P0 | Preview gate | Yes | Not started
TASK-0176 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Define experience goals and users — Buyer, seller and operations application shells | Define experience goals and users for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: experience brief | Buyer, seller and operations outcomes are measurable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0150 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0177 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Map jobs and complete journeys — Buyer, seller and operations application shells | Map jobs and complete journeys for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: journey map | Entry, decision, transaction and support moments are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0176 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0178 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Audit current screens — Buyer, seller and operations application shells | Audit current screens for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: screen-level gap audit | Confusion, missing states and misleading affordances are evidenced. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0177 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0179 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Design information architecture — Buyer, seller and operations application shells | Design information architecture for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: route and navigation model | Public, buyer, seller and operations navigation are separated. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0178 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0180 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Write content hierarchy and copy — Buyer, seller and operations application shells | Write content hierarchy and copy for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: content specification | The core transfer idea is understandable without insider terminology. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0179 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0181 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Define interaction principles — Buyer, seller and operations application shells | Define interaction principles for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: interaction contract | Progressive disclosure, confirmation and recovery are consistent. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0180 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0182 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Map data and state to UI — Buyer, seller and operations application shells | Map data and state to UI for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: UI state matrix | Every visual status maps to server-confirmed data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0181 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0183 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Define layout system — Buyer, seller and operations application shells | Define layout system for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: grid and spatial system | Content density, maximum widths and reading order are consistent. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0182 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0184 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Define responsive behavior — Buyer, seller and operations application shells | Define responsive behavior for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: breakpoint behavior | Mobile, tablet, desktop and ultra-wide layouts preserve task completion. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0183 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0185 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Create low-fidelity wireframes — Buyer, seller and operations application shells | Create low-fidelity wireframes for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: wireframe set | Critical flows and alternatives can be reviewed before visual polish. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0184 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0186 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Specify reusable components — Buyer, seller and operations application shells | Specify reusable components for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: component inventory | States, variants and ownership prevent one-off UI drift. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0185 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0187 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Define visual mood and tokens — Buyer, seller and operations application shells | Define visual mood and tokens for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: visual token set | Colour, typography, radius, shadow, image and motion choices are coherent. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0186 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0188 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Create high-fidelity designs — Buyer, seller and operations application shells | Create high-fidelity designs for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: high-fidelity screen set | Realistic content and complete states establish the quality bar. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0187 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0189 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Build an interactive prototype — Buyer, seller and operations application shells | Build an interactive prototype for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: reviewable prototype | Primary journeys, transitions and destination changes can be tested. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0188 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0190 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Complete accessibility review — Buyer, seller and operations application shells | Complete accessibility review for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: accessibility annotations | Keyboard, focus, semantics, errors, contrast and motion are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0189 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0191 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Implement design tokens — Buyer, seller and operations application shells | Implement design tokens for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: code-native design tokens | Tokens are typed, documented and usable across all workspaces. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0190 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0192 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Implement responsive components — Buyer, seller and operations application shells | Implement responsive components for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: shared component implementation | Components match approved states without page-specific forks. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0191 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0193 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Implement non-happy visual states — Buyer, seller and operations application shells | Implement non-happy visual states for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: complete state implementation | Loading, empty, stale, error and permission states are intentional. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0192 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0194 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Implement restrained motion — Buyer, seller and operations application shells | Implement restrained motion for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: motion system | Motion clarifies change and respects reduced-motion settings. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0193 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0195 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Write component tests — Buyer, seller and operations application shells | Write component tests for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: component test suite | Variants, keyboard behavior and state rendering are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0194 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0196 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Create visual regression coverage — Buyer, seller and operations application shells | Create visual regression coverage for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: visual baseline | Critical breakpoints and themes detect unintended drift. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0195 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0197 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Run usability testing — Buyer, seller and operations application shells | Run usability testing for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: usability findings | Representative users can complete the flow and understand status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0196 | Product Design Lead | P0 | Development / preview | Yes | Not started
TASK-0198 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Validate experience performance — Buyer, seller and operations application shells | Validate experience performance for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: UX performance report | Images, transitions and hydration meet interaction budgets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0197 | Product Design Lead | P0 | Development / preview | Yes | Not started
TASK-0199 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Publish design documentation — Buyer, seller and operations application shells | Publish design documentation for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: design system documentation | Design and engineering share one current source. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0198 | Product Design Lead | P0 | Development / preview | Yes | Not started
TASK-0200 | P04 — World-class design and dynamic experience | Buyer, seller and operations application shells | Pass design acceptance — Buyer, seller and operations application shells | Pass design acceptance for Buyer, seller and operations application shells. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer, seller and operations application shells: accepted experience evidence | Product, design, accessibility and engineering approve the preview. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0199 | Product Design Lead | P0 | Preview gate | Yes | Not started
TASK-0201 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Define experience goals and users — Location-aware visual theme engine | Define experience goals and users for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: experience brief | Buyer, seller and operations outcomes are measurable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0150 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0202 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Map jobs and complete journeys — Location-aware visual theme engine | Map jobs and complete journeys for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: journey map | Entry, decision, transaction and support moments are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0201 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0203 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Audit current screens — Location-aware visual theme engine | Audit current screens for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: screen-level gap audit | Confusion, missing states and misleading affordances are evidenced. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0202 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0204 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Design information architecture — Location-aware visual theme engine | Design information architecture for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: route and navigation model | Public, buyer, seller and operations navigation are separated. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0203 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0205 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Write content hierarchy and copy — Location-aware visual theme engine | Write content hierarchy and copy for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: content specification | The core transfer idea is understandable without insider terminology. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0204 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0206 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Define interaction principles — Location-aware visual theme engine | Define interaction principles for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: interaction contract | Progressive disclosure, confirmation and recovery are consistent. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0205 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0207 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Map data and state to UI — Location-aware visual theme engine | Map data and state to UI for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: UI state matrix | Every visual status maps to server-confirmed data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0206 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0208 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Define layout system — Location-aware visual theme engine | Define layout system for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: grid and spatial system | Content density, maximum widths and reading order are consistent. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0207 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0209 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Define responsive behavior — Location-aware visual theme engine | Define responsive behavior for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: breakpoint behavior | Mobile, tablet, desktop and ultra-wide layouts preserve task completion. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0208 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0210 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Create low-fidelity wireframes — Location-aware visual theme engine | Create low-fidelity wireframes for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: wireframe set | Critical flows and alternatives can be reviewed before visual polish. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0209 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0211 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Specify reusable components — Location-aware visual theme engine | Specify reusable components for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: component inventory | States, variants and ownership prevent one-off UI drift. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0210 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0212 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Define visual mood and tokens — Location-aware visual theme engine | Define visual mood and tokens for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: visual token set | Colour, typography, radius, shadow, image and motion choices are coherent. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0211 | Product Design Lead | P1 | Local / design | No | Not started
TASK-0213 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Create high-fidelity designs — Location-aware visual theme engine | Create high-fidelity designs for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: high-fidelity screen set | Realistic content and complete states establish the quality bar. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0212 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0214 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Build an interactive prototype — Location-aware visual theme engine | Build an interactive prototype for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: reviewable prototype | Primary journeys, transitions and destination changes can be tested. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0213 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0215 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Complete accessibility review — Location-aware visual theme engine | Complete accessibility review for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: accessibility annotations | Keyboard, focus, semantics, errors, contrast and motion are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0214 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0216 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Implement design tokens — Location-aware visual theme engine | Implement design tokens for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: code-native design tokens | Tokens are typed, documented and usable across all workspaces. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0215 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0217 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Implement responsive components — Location-aware visual theme engine | Implement responsive components for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: shared component implementation | Components match approved states without page-specific forks. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0216 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0218 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Implement non-happy visual states — Location-aware visual theme engine | Implement non-happy visual states for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: complete state implementation | Loading, empty, stale, error and permission states are intentional. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0217 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0219 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Implement restrained motion — Location-aware visual theme engine | Implement restrained motion for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: motion system | Motion clarifies change and respects reduced-motion settings. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0218 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0220 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Write component tests — Location-aware visual theme engine | Write component tests for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: component test suite | Variants, keyboard behavior and state rendering are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0219 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0221 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Create visual regression coverage — Location-aware visual theme engine | Create visual regression coverage for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: visual baseline | Critical breakpoints and themes detect unintended drift. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0220 | Product Design Lead | P1 | Development / preview | No | Not started
TASK-0222 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Run usability testing — Location-aware visual theme engine | Run usability testing for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: usability findings | Representative users can complete the flow and understand status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0221 | Product Design Lead | P0 | Development / preview | Yes | Not started
TASK-0223 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Validate experience performance — Location-aware visual theme engine | Validate experience performance for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: UX performance report | Images, transitions and hydration meet interaction budgets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0222 | Product Design Lead | P0 | Development / preview | Yes | Not started
TASK-0224 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Publish design documentation — Location-aware visual theme engine | Publish design documentation for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: design system documentation | Design and engineering share one current source. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0223 | Product Design Lead | P0 | Development / preview | Yes | Not started
TASK-0225 | P04 — World-class design and dynamic experience | Location-aware visual theme engine | Pass design acceptance — Location-aware visual theme engine | Pass design acceptance for Location-aware visual theme engine. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Location-aware visual theme engine: accepted experience evidence | Product, design, accessibility and engineering approve the preview. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0224, TASK-0175, TASK-0200 | Product Design Lead | P0 | Preview gate | Yes | Not started
TASK-0226 | P05 — Identity and access control | Customer identity and workspace switching | Define outcome and acceptance — Customer identity and workspace switching | Define outcome and acceptance for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0225 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0227 | P05 — Identity and access control | Customer identity and workspace switching | Trace controlling requirements — Customer identity and workspace switching | Trace controlling requirements for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0226 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0228 | P05 — Identity and access control | Customer identity and workspace switching | Audit the current implementation — Customer identity and workspace switching | Audit the current implementation for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0227 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0229 | P05 — Identity and access control | Customer identity and workspace switching | Write user stories and edge cases — Customer identity and workspace switching | Write user stories and edge cases for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0228 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0230 | P05 — Identity and access control | Customer identity and workspace switching | Model roles and permissions — Customer identity and workspace switching | Model roles and permissions for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0229 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0231 | P05 — Identity and access control | Customer identity and workspace switching | Design the data contract — Customer identity and workspace switching | Design the data contract for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0230 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0232 | P05 — Identity and access control | Customer identity and workspace switching | Define the state machine — Customer identity and workspace switching | Define the state machine for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0231 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0233 | P05 — Identity and access control | Customer identity and workspace switching | Define commands, queries and events — Customer identity and workspace switching | Define commands, queries and events for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0232 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0234 | P05 — Identity and access control | Customer identity and workspace switching | Map the complete UX flow — Customer identity and workspace switching | Map the complete UX flow for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0233 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0235 | P05 — Identity and access control | Customer identity and workspace switching | Create responsive wireframes — Customer identity and workspace switching | Create responsive wireframes for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0234 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0236 | P05 — Identity and access control | Customer identity and workspace switching | Complete high-fidelity design — Customer identity and workspace switching | Complete high-fidelity design for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0235 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0237 | P05 — Identity and access control | Customer identity and workspace switching | Specify accessibility behaviour — Customer identity and workspace switching | Specify accessibility behaviour for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0236 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0238 | P05 — Identity and access control | Customer identity and workspace switching | Implement schema and migrations — Customer identity and workspace switching | Implement schema and migrations for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0237 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0239 | P05 — Identity and access control | Customer identity and workspace switching | Implement server-side domain logic — Customer identity and workspace switching | Implement server-side domain logic for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0238 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0240 | P05 — Identity and access control | Customer identity and workspace switching | Implement the frontend foundation — Customer identity and workspace switching | Implement the frontend foundation for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0239 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0241 | P05 — Identity and access control | Customer identity and workspace switching | Implement the happy path — Customer identity and workspace switching | Implement the happy path for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0240 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0242 | P05 — Identity and access control | Customer identity and workspace switching | Implement non-happy states — Customer identity and workspace switching | Implement non-happy states for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0241 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0243 | P05 — Identity and access control | Customer identity and workspace switching | Add audit and observability — Customer identity and workspace switching | Add audit and observability for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0242 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0244 | P05 — Identity and access control | Customer identity and workspace switching | Apply security and privacy controls — Customer identity and workspace switching | Apply security and privacy controls for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0243 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0245 | P05 — Identity and access control | Customer identity and workspace switching | Write unit tests — Customer identity and workspace switching | Write unit tests for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0244 | Identity and Security Engineer | P0 | Development / preview | Yes | Not started
TASK-0246 | P05 — Identity and access control | Customer identity and workspace switching | Write integration tests — Customer identity and workspace switching | Write integration tests for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0245 | Identity and Security Engineer | P0 | Development / preview | Yes | Not started
TASK-0247 | P05 — Identity and access control | Customer identity and workspace switching | Write end-to-end tests — Customer identity and workspace switching | Write end-to-end tests for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0246 | Identity and Security Engineer | P0 | Development / preview | Yes | Not started
TASK-0248 | P05 — Identity and access control | Customer identity and workspace switching | Validate performance and resilience — Customer identity and workspace switching | Validate performance and resilience for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0247 | Identity and Security Engineer | P0 | Development / preview | Yes | Not started
TASK-0249 | P05 — Identity and access control | Customer identity and workspace switching | Publish operating documentation — Customer identity and workspace switching | Publish operating documentation for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0248 | Identity and Security Engineer | P0 | Development / preview | Yes | Not started
TASK-0250 | P05 — Identity and access control | Customer identity and workspace switching | Pass preview acceptance — Customer identity and workspace switching | Pass preview acceptance for Customer identity and workspace switching. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Customer identity and workspace switching: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0249 | Identity and Security Engineer | P0 | Preview gate | Yes | Not started
TASK-0251 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Define outcome and acceptance — Operations RBAC, MFA and privileged access | Define outcome and acceptance for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0225 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0252 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Trace controlling requirements — Operations RBAC, MFA and privileged access | Trace controlling requirements for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0251 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0253 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Audit the current implementation — Operations RBAC, MFA and privileged access | Audit the current implementation for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0252 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0254 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Write user stories and edge cases — Operations RBAC, MFA and privileged access | Write user stories and edge cases for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0253 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0255 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Model roles and permissions — Operations RBAC, MFA and privileged access | Model roles and permissions for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0254 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0256 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Design the data contract — Operations RBAC, MFA and privileged access | Design the data contract for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0255 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0257 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Define the state machine — Operations RBAC, MFA and privileged access | Define the state machine for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0256 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0258 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Define commands, queries and events — Operations RBAC, MFA and privileged access | Define commands, queries and events for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0257 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0259 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Map the complete UX flow — Operations RBAC, MFA and privileged access | Map the complete UX flow for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0258 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0260 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Create responsive wireframes — Operations RBAC, MFA and privileged access | Create responsive wireframes for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0259 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0261 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Complete high-fidelity design — Operations RBAC, MFA and privileged access | Complete high-fidelity design for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0260 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0262 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Specify accessibility behaviour — Operations RBAC, MFA and privileged access | Specify accessibility behaviour for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0261 | Identity and Security Engineer | P1 | Local / design | No | Not started
TASK-0263 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Implement schema and migrations — Operations RBAC, MFA and privileged access | Implement schema and migrations for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0262 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0264 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Implement server-side domain logic — Operations RBAC, MFA and privileged access | Implement server-side domain logic for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0263 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0265 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Implement the frontend foundation — Operations RBAC, MFA and privileged access | Implement the frontend foundation for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0264 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0266 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Implement the happy path — Operations RBAC, MFA and privileged access | Implement the happy path for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0265 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0267 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Implement non-happy states — Operations RBAC, MFA and privileged access | Implement non-happy states for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0266 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0268 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Add audit and observability — Operations RBAC, MFA and privileged access | Add audit and observability for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0267 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0269 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Apply security and privacy controls — Operations RBAC, MFA and privileged access | Apply security and privacy controls for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0268 | Identity and Security Engineer | P1 | Development / preview | No | Not started
TASK-0270 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Write unit tests — Operations RBAC, MFA and privileged access | Write unit tests for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0269 | Identity and Security Engineer | P0 | Development / preview | Yes | Not started
TASK-0271 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Write integration tests — Operations RBAC, MFA and privileged access | Write integration tests for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0270 | Identity and Security Engineer | P0 | Development / preview | Yes | Not started
TASK-0272 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Write end-to-end tests — Operations RBAC, MFA and privileged access | Write end-to-end tests for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0271 | Identity and Security Engineer | P0 | Development / preview | Yes | Not started
TASK-0273 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Validate performance and resilience — Operations RBAC, MFA and privileged access | Validate performance and resilience for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0272 | Identity and Security Engineer | P0 | Development / preview | Yes | Not started
TASK-0274 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Publish operating documentation — Operations RBAC, MFA and privileged access | Publish operating documentation for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0273 | Identity and Security Engineer | P0 | Development / preview | Yes | Not started
TASK-0275 | P05 — Identity and access control | Operations RBAC, MFA and privileged access | Pass preview acceptance — Operations RBAC, MFA and privileged access | Pass preview acceptance for Operations RBAC, MFA and privileged access. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Operations RBAC, MFA and privileged access: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0274, TASK-0250 | Identity and Security Engineer | P0 | Preview gate | Yes | Not started
TASK-0276 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Define outcome and acceptance — Destination selection and Google Maps integration | Define outcome and acceptance for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0275 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0277 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Trace controlling requirements — Destination selection and Google Maps integration | Trace controlling requirements for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0276 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0278 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Audit the current implementation — Destination selection and Google Maps integration | Audit the current implementation for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0277 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0279 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Write user stories and edge cases — Destination selection and Google Maps integration | Write user stories and edge cases for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0278 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0280 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Model roles and permissions — Destination selection and Google Maps integration | Model roles and permissions for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0279 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0281 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Design the data contract — Destination selection and Google Maps integration | Design the data contract for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0280 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0282 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Define the state machine — Destination selection and Google Maps integration | Define the state machine for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0281 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0283 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Define commands, queries and events — Destination selection and Google Maps integration | Define commands, queries and events for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0282 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0284 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Map the complete UX flow — Destination selection and Google Maps integration | Map the complete UX flow for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0283 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0285 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Create responsive wireframes — Destination selection and Google Maps integration | Create responsive wireframes for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0284 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0286 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Complete high-fidelity design — Destination selection and Google Maps integration | Complete high-fidelity design for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0285 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0287 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Specify accessibility behaviour — Destination selection and Google Maps integration | Specify accessibility behaviour for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0286 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0288 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Implement schema and migrations — Destination selection and Google Maps integration | Implement schema and migrations for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0287 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0289 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Implement server-side domain logic — Destination selection and Google Maps integration | Implement server-side domain logic for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0288 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0290 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Implement the frontend foundation — Destination selection and Google Maps integration | Implement the frontend foundation for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0289 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0291 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Implement the happy path — Destination selection and Google Maps integration | Implement the happy path for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0290 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0292 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Implement non-happy states — Destination selection and Google Maps integration | Implement non-happy states for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0291 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0293 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Add audit and observability — Destination selection and Google Maps integration | Add audit and observability for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0292 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0294 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Apply security and privacy controls — Destination selection and Google Maps integration | Apply security and privacy controls for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0293 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0295 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Write unit tests — Destination selection and Google Maps integration | Write unit tests for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0294 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0296 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Write integration tests — Destination selection and Google Maps integration | Write integration tests for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0295 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0297 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Write end-to-end tests — Destination selection and Google Maps integration | Write end-to-end tests for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0296 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0298 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Validate performance and resilience — Destination selection and Google Maps integration | Validate performance and resilience for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0297 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0299 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Publish operating documentation — Destination selection and Google Maps integration | Publish operating documentation for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0298 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0300 | P06 — Location, maps and property catalogue | Destination selection and Google Maps integration | Pass preview acceptance — Destination selection and Google Maps integration | Pass preview acceptance for Destination selection and Google Maps integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Destination selection and Google Maps integration: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0299 | Location Platform Engineer | P0 | Preview gate | Yes | Not started
TASK-0301 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Define outcome and acceptance — Canonical property and address catalogue | Define outcome and acceptance for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0275 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0302 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Trace controlling requirements — Canonical property and address catalogue | Trace controlling requirements for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0301 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0303 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Audit the current implementation — Canonical property and address catalogue | Audit the current implementation for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0302 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0304 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Write user stories and edge cases — Canonical property and address catalogue | Write user stories and edge cases for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0303 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0305 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Model roles and permissions — Canonical property and address catalogue | Model roles and permissions for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0304 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0306 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Design the data contract — Canonical property and address catalogue | Design the data contract for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0305 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0307 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Define the state machine — Canonical property and address catalogue | Define the state machine for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0306 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0308 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Define commands, queries and events — Canonical property and address catalogue | Define commands, queries and events for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0307 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0309 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Map the complete UX flow — Canonical property and address catalogue | Map the complete UX flow for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0308 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0310 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Create responsive wireframes — Canonical property and address catalogue | Create responsive wireframes for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0309 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0311 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Complete high-fidelity design — Canonical property and address catalogue | Complete high-fidelity design for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0310 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0312 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Specify accessibility behaviour — Canonical property and address catalogue | Specify accessibility behaviour for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0311 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0313 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Implement schema and migrations — Canonical property and address catalogue | Implement schema and migrations for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0312 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0314 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Implement server-side domain logic — Canonical property and address catalogue | Implement server-side domain logic for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0313 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0315 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Implement the frontend foundation — Canonical property and address catalogue | Implement the frontend foundation for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0314 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0316 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Implement the happy path — Canonical property and address catalogue | Implement the happy path for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0315 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0317 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Implement non-happy states — Canonical property and address catalogue | Implement non-happy states for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0316 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0318 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Add audit and observability — Canonical property and address catalogue | Add audit and observability for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0317 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0319 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Apply security and privacy controls — Canonical property and address catalogue | Apply security and privacy controls for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0318 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0320 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Write unit tests — Canonical property and address catalogue | Write unit tests for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0319 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0321 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Write integration tests — Canonical property and address catalogue | Write integration tests for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0320 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0322 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Write end-to-end tests — Canonical property and address catalogue | Write end-to-end tests for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0321 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0323 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Validate performance and resilience — Canonical property and address catalogue | Validate performance and resilience for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0322 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0324 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Publish operating documentation — Canonical property and address catalogue | Publish operating documentation for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0323 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0325 | P06 — Location, maps and property catalogue | Canonical property and address catalogue | Pass preview acceptance — Canonical property and address catalogue | Pass preview acceptance for Canonical property and address catalogue. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and address catalogue: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0324 | Location Platform Engineer | P0 | Preview gate | Yes | Not started
TASK-0326 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Define outcome and acceptance — PostGIS radius search and map-list consistency | Define outcome and acceptance for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0275 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0327 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Trace controlling requirements — PostGIS radius search and map-list consistency | Trace controlling requirements for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0326 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0328 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Audit the current implementation — PostGIS radius search and map-list consistency | Audit the current implementation for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0327 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0329 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Write user stories and edge cases — PostGIS radius search and map-list consistency | Write user stories and edge cases for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0328 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0330 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Model roles and permissions — PostGIS radius search and map-list consistency | Model roles and permissions for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0329 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0331 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Design the data contract — PostGIS radius search and map-list consistency | Design the data contract for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0330 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0332 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Define the state machine — PostGIS radius search and map-list consistency | Define the state machine for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0331 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0333 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Define commands, queries and events — PostGIS radius search and map-list consistency | Define commands, queries and events for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0332 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0334 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Map the complete UX flow — PostGIS radius search and map-list consistency | Map the complete UX flow for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0333 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0335 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Create responsive wireframes — PostGIS radius search and map-list consistency | Create responsive wireframes for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0334 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0336 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Complete high-fidelity design — PostGIS radius search and map-list consistency | Complete high-fidelity design for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0335 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0337 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Specify accessibility behaviour — PostGIS radius search and map-list consistency | Specify accessibility behaviour for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0336 | Location Platform Engineer | P1 | Local / design | No | Not started
TASK-0338 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Implement schema and migrations — PostGIS radius search and map-list consistency | Implement schema and migrations for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0337 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0339 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Implement server-side domain logic — PostGIS radius search and map-list consistency | Implement server-side domain logic for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0338 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0340 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Implement the frontend foundation — PostGIS radius search and map-list consistency | Implement the frontend foundation for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0339 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0341 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Implement the happy path — PostGIS radius search and map-list consistency | Implement the happy path for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0340 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0342 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Implement non-happy states — PostGIS radius search and map-list consistency | Implement non-happy states for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0341 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0343 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Add audit and observability — PostGIS radius search and map-list consistency | Add audit and observability for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0342 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0344 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Apply security and privacy controls — PostGIS radius search and map-list consistency | Apply security and privacy controls for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0343 | Location Platform Engineer | P1 | Development / preview | No | Not started
TASK-0345 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Write unit tests — PostGIS radius search and map-list consistency | Write unit tests for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0344 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0346 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Write integration tests — PostGIS radius search and map-list consistency | Write integration tests for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0345 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0347 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Write end-to-end tests — PostGIS radius search and map-list consistency | Write end-to-end tests for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0346 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0348 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Validate performance and resilience — PostGIS radius search and map-list consistency | Validate performance and resilience for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0347 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0349 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Publish operating documentation — PostGIS radius search and map-list consistency | Publish operating documentation for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0348 | Location Platform Engineer | P0 | Development / preview | Yes | Not started
TASK-0350 | P06 — Location, maps and property catalogue | PostGIS radius search and map-list consistency | Pass preview acceptance — PostGIS radius search and map-list consistency | Pass preview acceptance for PostGIS radius search and map-list consistency. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | PostGIS radius search and map-list consistency: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0349, TASK-0300, TASK-0325 | Location Platform Engineer | P0 | Preview gate | Yes | Not started
TASK-0351 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Inventory the supplied image prompt — Recovery and governance of approximately 140 supplied prompts | Inventory the supplied image prompt for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: prompt inventory entry | The original prompt is preserved verbatim with provenance. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0350 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0352 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Map the image to a product slot — Recovery and governance of approximately 140 supplied prompts | Map the image to a product slot for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: page and slot mapping | Destination, route, component and purpose are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0351 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0353 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Verify rights and permitted use — Recovery and governance of approximately 140 supplied prompts | Verify rights and permitted use for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: rights record | Unknown rights block publication. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0352 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0354 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Classify real, editorial or generated content — Recovery and governance of approximately 140 supplied prompts | Classify real, editorial or generated content for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: content classification | Generated imagery cannot appear as real property inventory. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0353 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0355 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Rewrite the production prompt — Recovery and governance of approximately 140 supplied prompts | Rewrite the production prompt for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: production-ready prompt | Composition, subject, culture, season, light and exclusions are precise. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0354 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0356 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Apply brand constraints — Recovery and governance of approximately 140 supplied prompts | Apply brand constraints for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: brand-aligned prompt | The result supports StayRelay without embedded logos or text. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0355 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0357 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Add location-specific context — Recovery and governance of approximately 140 supplied prompts | Add location-specific context for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: destination context | Architecture and landscape are plausible without false factual claims. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0356 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0358 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Add negative prompt and safety rules — Recovery and governance of approximately 140 supplied prompts | Add negative prompt and safety rules for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: negative-prompt specification | Artifacts, stereotypes, fake documents and misleading details are excluded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0357 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0359 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Generate controlled draft variants — Recovery and governance of approximately 140 supplied prompts | Generate controlled draft variants for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: draft image set | Variants use the approved tool, model and recorded settings. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0358 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0360 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Review factual and cultural plausibility — Recovery and governance of approximately 140 supplied prompts | Review factual and cultural plausibility for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: plausibility review | Materially inaccurate or insensitive imagery is rejected. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0359 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0361 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Review diversity and representation — Recovery and governance of approximately 140 supplied prompts | Review diversity and representation for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: representation review | People and places avoid tokenism and repetitive stock imagery. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0360 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0362 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Select the approved master — Recovery and governance of approximately 140 supplied prompts | Select the approved master for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: approved master image | Selection rationale and reviewer are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0361 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0363 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Complete professional image editing — Recovery and governance of approximately 140 supplied prompts | Complete professional image editing for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: retouched master | Colour, artifacts and distractions are corrected without deceptive alteration. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0362 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0364 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Create responsive crops — Recovery and governance of approximately 140 supplied prompts | Create responsive crops for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: responsive crop set | Hero, card, mobile and social crops preserve the focal subject. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0363 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0365 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Write accessible alt text — Recovery and governance of approximately 140 supplied prompts | Write accessible alt text for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: approved alt text | Alt text describes purpose without marketing filler. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0364 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0366 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Attach provenance metadata — Recovery and governance of approximately 140 supplied prompts | Attach provenance metadata for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: asset metadata | Prompt, model, rights, reviewer, checksum and destination are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0365 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0367 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Optimize formats and size — Recovery and governance of approximately 140 supplied prompts | Optimize formats and size for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: AVIF, WebP and fallback variants | Visual quality meets the assigned performance budget. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0366 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0368 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Upload to the approved media store — Recovery and governance of approximately 140 supplied prompts | Upload to the approved media store for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: stored asset and stable reference | The asset is private or public according to policy and is not duplicated. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0367 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0369 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Update the asset manifest — Recovery and governance of approximately 140 supplied prompts | Update the asset manifest for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: manifest entry | Every derivative resolves to one approved master and version. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0368 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0370 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Bind the asset to the component — Recovery and governance of approximately 140 supplied prompts | Bind the asset to the component for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: runtime component mapping | Only the intended route, destination and slot can select the asset. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0369 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0371 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Implement missing-asset fallback — Recovery and governance of approximately 140 supplied prompts | Implement missing-asset fallback for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: accessible fallback behavior | A missing or rejected asset never breaks layout or misrepresents a property. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0370 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0372 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Validate responsive delivery — Recovery and governance of approximately 140 supplied prompts | Validate responsive delivery for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: responsive delivery test | Correct format, density and crop load at each breakpoint. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0371 | Creative Technology Lead | P0 | Development / preview | Yes | Not started
TASK-0373 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Validate image performance — Recovery and governance of approximately 140 supplied prompts | Validate image performance for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: image performance evidence | LCP, caching and transfer size meet the route budget. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0372 | Creative Technology Lead | P0 | Development / preview | Yes | Not started
TASK-0374 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Complete moderation and final review — Recovery and governance of approximately 140 supplied prompts | Complete moderation and final review for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: moderation approval | Safety, rights, truthfulness and brand checks pass. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0373 | Creative Technology Lead | P0 | Development / preview | Yes | Not started
TASK-0375 | P07 — Media and 140-image production pipeline | Recovery and governance of approximately 140 supplied prompts | Pass asset acceptance — Recovery and governance of approximately 140 supplied prompts | Pass asset acceptance for Recovery and governance of approximately 140 supplied prompts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery and governance of approximately 140 supplied prompts: accepted production asset | The approved image is visible in preview with metadata and fallback tested. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0374 | Creative Technology Lead | P0 | Preview gate | Yes | Not started
TASK-0376 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Inventory the supplied image prompt — Canva and image-generation production review | Inventory the supplied image prompt for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: prompt inventory entry | The original prompt is preserved verbatim with provenance. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0350 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0377 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Map the image to a product slot — Canva and image-generation production review | Map the image to a product slot for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: page and slot mapping | Destination, route, component and purpose are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0376 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0378 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Verify rights and permitted use — Canva and image-generation production review | Verify rights and permitted use for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: rights record | Unknown rights block publication. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0377 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0379 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Classify real, editorial or generated content — Canva and image-generation production review | Classify real, editorial or generated content for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: content classification | Generated imagery cannot appear as real property inventory. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0378 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0380 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Rewrite the production prompt — Canva and image-generation production review | Rewrite the production prompt for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: production-ready prompt | Composition, subject, culture, season, light and exclusions are precise. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0379 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0381 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Apply brand constraints — Canva and image-generation production review | Apply brand constraints for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: brand-aligned prompt | The result supports StayRelay without embedded logos or text. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0380 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0382 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Add location-specific context — Canva and image-generation production review | Add location-specific context for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: destination context | Architecture and landscape are plausible without false factual claims. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0381 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0383 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Add negative prompt and safety rules — Canva and image-generation production review | Add negative prompt and safety rules for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: negative-prompt specification | Artifacts, stereotypes, fake documents and misleading details are excluded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0382 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0384 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Generate controlled draft variants — Canva and image-generation production review | Generate controlled draft variants for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: draft image set | Variants use the approved tool, model and recorded settings. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0383 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0385 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Review factual and cultural plausibility — Canva and image-generation production review | Review factual and cultural plausibility for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: plausibility review | Materially inaccurate or insensitive imagery is rejected. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0384 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0386 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Review diversity and representation — Canva and image-generation production review | Review diversity and representation for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: representation review | People and places avoid tokenism and repetitive stock imagery. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0385 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0387 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Select the approved master — Canva and image-generation production review | Select the approved master for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: approved master image | Selection rationale and reviewer are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0386 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0388 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Complete professional image editing — Canva and image-generation production review | Complete professional image editing for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: retouched master | Colour, artifacts and distractions are corrected without deceptive alteration. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0387 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0389 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Create responsive crops — Canva and image-generation production review | Create responsive crops for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: responsive crop set | Hero, card, mobile and social crops preserve the focal subject. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0388 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0390 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Write accessible alt text — Canva and image-generation production review | Write accessible alt text for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: approved alt text | Alt text describes purpose without marketing filler. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0389 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0391 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Attach provenance metadata — Canva and image-generation production review | Attach provenance metadata for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: asset metadata | Prompt, model, rights, reviewer, checksum and destination are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0390 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0392 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Optimize formats and size — Canva and image-generation production review | Optimize formats and size for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: AVIF, WebP and fallback variants | Visual quality meets the assigned performance budget. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0391 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0393 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Upload to the approved media store — Canva and image-generation production review | Upload to the approved media store for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: stored asset and stable reference | The asset is private or public according to policy and is not duplicated. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0392 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0394 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Update the asset manifest — Canva and image-generation production review | Update the asset manifest for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: manifest entry | Every derivative resolves to one approved master and version. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0393 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0395 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Bind the asset to the component — Canva and image-generation production review | Bind the asset to the component for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: runtime component mapping | Only the intended route, destination and slot can select the asset. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0394 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0396 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Implement missing-asset fallback — Canva and image-generation production review | Implement missing-asset fallback for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: accessible fallback behavior | A missing or rejected asset never breaks layout or misrepresents a property. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0395 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0397 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Validate responsive delivery — Canva and image-generation production review | Validate responsive delivery for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: responsive delivery test | Correct format, density and crop load at each breakpoint. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0396 | Creative Technology Lead | P0 | Development / preview | Yes | Not started
TASK-0398 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Validate image performance — Canva and image-generation production review | Validate image performance for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: image performance evidence | LCP, caching and transfer size meet the route budget. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0397 | Creative Technology Lead | P0 | Development / preview | Yes | Not started
TASK-0399 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Complete moderation and final review — Canva and image-generation production review | Complete moderation and final review for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: moderation approval | Safety, rights, truthfulness and brand checks pass. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0398 | Creative Technology Lead | P0 | Development / preview | Yes | Not started
TASK-0400 | P07 — Media and 140-image production pipeline | Canva and image-generation production review | Pass asset acceptance — Canva and image-generation production review | Pass asset acceptance for Canva and image-generation production review. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canva and image-generation production review: accepted production asset | The approved image is visible in preview with metadata and fallback tested. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0399 | Creative Technology Lead | P0 | Preview gate | Yes | Not started
TASK-0401 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Inventory the supplied image prompt — Media upload, optimization and runtime selection | Inventory the supplied image prompt for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: prompt inventory entry | The original prompt is preserved verbatim with provenance. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0350 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0402 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Map the image to a product slot — Media upload, optimization and runtime selection | Map the image to a product slot for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: page and slot mapping | Destination, route, component and purpose are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0401 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0403 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Verify rights and permitted use — Media upload, optimization and runtime selection | Verify rights and permitted use for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: rights record | Unknown rights block publication. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0402 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0404 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Classify real, editorial or generated content — Media upload, optimization and runtime selection | Classify real, editorial or generated content for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: content classification | Generated imagery cannot appear as real property inventory. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0403 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0405 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Rewrite the production prompt — Media upload, optimization and runtime selection | Rewrite the production prompt for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: production-ready prompt | Composition, subject, culture, season, light and exclusions are precise. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0404 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0406 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Apply brand constraints — Media upload, optimization and runtime selection | Apply brand constraints for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: brand-aligned prompt | The result supports StayRelay without embedded logos or text. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0405 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0407 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Add location-specific context — Media upload, optimization and runtime selection | Add location-specific context for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: destination context | Architecture and landscape are plausible without false factual claims. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0406 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0408 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Add negative prompt and safety rules — Media upload, optimization and runtime selection | Add negative prompt and safety rules for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: negative-prompt specification | Artifacts, stereotypes, fake documents and misleading details are excluded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0407 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0409 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Generate controlled draft variants — Media upload, optimization and runtime selection | Generate controlled draft variants for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: draft image set | Variants use the approved tool, model and recorded settings. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0408 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0410 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Review factual and cultural plausibility — Media upload, optimization and runtime selection | Review factual and cultural plausibility for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: plausibility review | Materially inaccurate or insensitive imagery is rejected. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0409 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0411 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Review diversity and representation — Media upload, optimization and runtime selection | Review diversity and representation for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: representation review | People and places avoid tokenism and repetitive stock imagery. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0410 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0412 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Select the approved master — Media upload, optimization and runtime selection | Select the approved master for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: approved master image | Selection rationale and reviewer are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0411 | Creative Technology Lead | P1 | Local / design | No | Not started
TASK-0413 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Complete professional image editing — Media upload, optimization and runtime selection | Complete professional image editing for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: retouched master | Colour, artifacts and distractions are corrected without deceptive alteration. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0412 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0414 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Create responsive crops — Media upload, optimization and runtime selection | Create responsive crops for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: responsive crop set | Hero, card, mobile and social crops preserve the focal subject. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0413 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0415 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Write accessible alt text — Media upload, optimization and runtime selection | Write accessible alt text for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: approved alt text | Alt text describes purpose without marketing filler. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0414 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0416 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Attach provenance metadata — Media upload, optimization and runtime selection | Attach provenance metadata for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: asset metadata | Prompt, model, rights, reviewer, checksum and destination are recorded. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0415 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0417 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Optimize formats and size — Media upload, optimization and runtime selection | Optimize formats and size for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: AVIF, WebP and fallback variants | Visual quality meets the assigned performance budget. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0416 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0418 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Upload to the approved media store — Media upload, optimization and runtime selection | Upload to the approved media store for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: stored asset and stable reference | The asset is private or public according to policy and is not duplicated. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0417 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0419 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Update the asset manifest — Media upload, optimization and runtime selection | Update the asset manifest for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: manifest entry | Every derivative resolves to one approved master and version. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0418 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0420 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Bind the asset to the component — Media upload, optimization and runtime selection | Bind the asset to the component for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: runtime component mapping | Only the intended route, destination and slot can select the asset. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0419 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0421 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Implement missing-asset fallback — Media upload, optimization and runtime selection | Implement missing-asset fallback for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: accessible fallback behavior | A missing or rejected asset never breaks layout or misrepresents a property. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0420 | Creative Technology Lead | P1 | Development / preview | No | Not started
TASK-0422 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Validate responsive delivery — Media upload, optimization and runtime selection | Validate responsive delivery for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: responsive delivery test | Correct format, density and crop load at each breakpoint. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0421 | Creative Technology Lead | P0 | Development / preview | Yes | Not started
TASK-0423 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Validate image performance — Media upload, optimization and runtime selection | Validate image performance for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: image performance evidence | LCP, caching and transfer size meet the route budget. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0422 | Creative Technology Lead | P0 | Development / preview | Yes | Not started
TASK-0424 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Complete moderation and final review — Media upload, optimization and runtime selection | Complete moderation and final review for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: moderation approval | Safety, rights, truthfulness and brand checks pass. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0423 | Creative Technology Lead | P0 | Development / preview | Yes | Not started
TASK-0425 | P07 — Media and 140-image production pipeline | Media upload, optimization and runtime selection | Pass asset acceptance — Media upload, optimization and runtime selection | Pass asset acceptance for Media upload, optimization and runtime selection. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Media upload, optimization and runtime selection: accepted production asset | The approved image is visible in preview with metadata and fallback tested. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0424, TASK-0375, TASK-0400 | Creative Technology Lead | P0 | Preview gate | Yes | Not started
TASK-0426 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Define outcome and acceptance — Reservation intake wizard | Define outcome and acceptance for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0425 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0427 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Trace controlling requirements — Reservation intake wizard | Trace controlling requirements for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0426 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0428 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Audit the current implementation — Reservation intake wizard | Audit the current implementation for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0427 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0429 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Write user stories and edge cases — Reservation intake wizard | Write user stories and edge cases for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0428 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0430 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Model roles and permissions — Reservation intake wizard | Model roles and permissions for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0429 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0431 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Design the data contract — Reservation intake wizard | Design the data contract for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0430 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0432 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Define the state machine — Reservation intake wizard | Define the state machine for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0431 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0433 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Define commands, queries and events — Reservation intake wizard | Define commands, queries and events for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0432 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0434 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Map the complete UX flow — Reservation intake wizard | Map the complete UX flow for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0433 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0435 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Create responsive wireframes — Reservation intake wizard | Create responsive wireframes for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0434 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0436 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Complete high-fidelity design — Reservation intake wizard | Complete high-fidelity design for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0435 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0437 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Specify accessibility behaviour — Reservation intake wizard | Specify accessibility behaviour for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0436 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0438 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Implement schema and migrations — Reservation intake wizard | Implement schema and migrations for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0437 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0439 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Implement server-side domain logic — Reservation intake wizard | Implement server-side domain logic for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0438 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0440 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Implement the frontend foundation — Reservation intake wizard | Implement the frontend foundation for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0439 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0441 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Implement the happy path — Reservation intake wizard | Implement the happy path for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0440 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0442 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Implement non-happy states — Reservation intake wizard | Implement non-happy states for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0441 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0443 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Add audit and observability — Reservation intake wizard | Add audit and observability for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0442 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0444 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Apply security and privacy controls — Reservation intake wizard | Apply security and privacy controls for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0443 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0445 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Write unit tests — Reservation intake wizard | Write unit tests for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0444 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0446 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Write integration tests — Reservation intake wizard | Write integration tests for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0445 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0447 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Write end-to-end tests — Reservation intake wizard | Write end-to-end tests for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0446 | Seller Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0448 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Validate performance and resilience — Reservation intake wizard | Validate performance and resilience for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0447 | Seller Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0449 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Publish operating documentation — Reservation intake wizard | Publish operating documentation for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0448 | Seller Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0450 | P08 — Seller reservation and listing workflow | Reservation intake wizard | Pass preview acceptance — Reservation intake wizard | Pass preview acceptance for Reservation intake wizard. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Reservation intake wizard: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0449 | Seller Product Engineer | P0 | Preview gate | Yes | Not started
TASK-0451 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Define outcome and acceptance — Private evidence upload and verification status | Define outcome and acceptance for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0425 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0452 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Trace controlling requirements — Private evidence upload and verification status | Trace controlling requirements for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0451 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0453 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Audit the current implementation — Private evidence upload and verification status | Audit the current implementation for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0452 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0454 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Write user stories and edge cases — Private evidence upload and verification status | Write user stories and edge cases for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0453 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0455 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Model roles and permissions — Private evidence upload and verification status | Model roles and permissions for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0454 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0456 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Design the data contract — Private evidence upload and verification status | Design the data contract for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0455 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0457 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Define the state machine — Private evidence upload and verification status | Define the state machine for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0456 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0458 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Define commands, queries and events — Private evidence upload and verification status | Define commands, queries and events for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0457 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0459 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Map the complete UX flow — Private evidence upload and verification status | Map the complete UX flow for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0458 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0460 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Create responsive wireframes — Private evidence upload and verification status | Create responsive wireframes for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0459 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0461 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Complete high-fidelity design — Private evidence upload and verification status | Complete high-fidelity design for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0460 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0462 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Specify accessibility behaviour — Private evidence upload and verification status | Specify accessibility behaviour for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0461 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0463 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Implement schema and migrations — Private evidence upload and verification status | Implement schema and migrations for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0462 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0464 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Implement server-side domain logic — Private evidence upload and verification status | Implement server-side domain logic for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0463 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0465 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Implement the frontend foundation — Private evidence upload and verification status | Implement the frontend foundation for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0464 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0466 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Implement the happy path — Private evidence upload and verification status | Implement the happy path for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0465 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0467 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Implement non-happy states — Private evidence upload and verification status | Implement non-happy states for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0466 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0468 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Add audit and observability — Private evidence upload and verification status | Add audit and observability for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0467 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0469 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Apply security and privacy controls — Private evidence upload and verification status | Apply security and privacy controls for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0468 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0470 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Write unit tests — Private evidence upload and verification status | Write unit tests for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0469 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0471 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Write integration tests — Private evidence upload and verification status | Write integration tests for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0470 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0472 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Write end-to-end tests — Private evidence upload and verification status | Write end-to-end tests for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0471 | Seller Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0473 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Validate performance and resilience — Private evidence upload and verification status | Validate performance and resilience for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0472 | Seller Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0474 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Publish operating documentation — Private evidence upload and verification status | Publish operating documentation for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0473 | Seller Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0475 | P08 — Seller reservation and listing workflow | Private evidence upload and verification status | Pass preview acceptance — Private evidence upload and verification status | Pass preview acceptance for Private evidence upload and verification status. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Private evidence upload and verification status: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0474 | Seller Product Engineer | P0 | Preview gate | Yes | Not started
TASK-0476 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Define outcome and acceptance — Seller listing, transfer task and payout workspace | Define outcome and acceptance for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0425 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0477 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Trace controlling requirements — Seller listing, transfer task and payout workspace | Trace controlling requirements for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0476 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0478 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Audit the current implementation — Seller listing, transfer task and payout workspace | Audit the current implementation for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0477 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0479 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Write user stories and edge cases — Seller listing, transfer task and payout workspace | Write user stories and edge cases for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0478 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0480 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Model roles and permissions — Seller listing, transfer task and payout workspace | Model roles and permissions for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0479 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0481 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Design the data contract — Seller listing, transfer task and payout workspace | Design the data contract for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0480 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0482 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Define the state machine — Seller listing, transfer task and payout workspace | Define the state machine for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0481 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0483 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Define commands, queries and events — Seller listing, transfer task and payout workspace | Define commands, queries and events for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0482 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0484 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Map the complete UX flow — Seller listing, transfer task and payout workspace | Map the complete UX flow for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0483 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0485 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Create responsive wireframes — Seller listing, transfer task and payout workspace | Create responsive wireframes for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0484 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0486 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Complete high-fidelity design — Seller listing, transfer task and payout workspace | Complete high-fidelity design for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0485 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0487 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Specify accessibility behaviour — Seller listing, transfer task and payout workspace | Specify accessibility behaviour for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0486 | Seller Product Engineer | P1 | Local / design | No | Not started
TASK-0488 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Implement schema and migrations — Seller listing, transfer task and payout workspace | Implement schema and migrations for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0487 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0489 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Implement server-side domain logic — Seller listing, transfer task and payout workspace | Implement server-side domain logic for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0488 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0490 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Implement the frontend foundation — Seller listing, transfer task and payout workspace | Implement the frontend foundation for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0489 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0491 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Implement the happy path — Seller listing, transfer task and payout workspace | Implement the happy path for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0490 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0492 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Implement non-happy states — Seller listing, transfer task and payout workspace | Implement non-happy states for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0491 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0493 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Add audit and observability — Seller listing, transfer task and payout workspace | Add audit and observability for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0492 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0494 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Apply security and privacy controls — Seller listing, transfer task and payout workspace | Apply security and privacy controls for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0493 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0495 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Write unit tests — Seller listing, transfer task and payout workspace | Write unit tests for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0494 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0496 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Write integration tests — Seller listing, transfer task and payout workspace | Write integration tests for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0495 | Seller Product Engineer | P1 | Development / preview | No | Not started
TASK-0497 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Write end-to-end tests — Seller listing, transfer task and payout workspace | Write end-to-end tests for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0496 | Seller Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0498 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Validate performance and resilience — Seller listing, transfer task and payout workspace | Validate performance and resilience for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0497 | Seller Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0499 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Publish operating documentation — Seller listing, transfer task and payout workspace | Publish operating documentation for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0498 | Seller Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0500 | P08 — Seller reservation and listing workflow | Seller listing, transfer task and payout workspace | Pass preview acceptance — Seller listing, transfer task and payout workspace | Pass preview acceptance for Seller listing, transfer task and payout workspace. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Seller listing, transfer task and payout workspace: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0499, TASK-0450, TASK-0475 | Seller Product Engineer | P0 | Preview gate | Yes | Not started
TASK-0501 | P09 — Operations and administration | Evidence, policy and eligibility operations | Define outcome and acceptance — Evidence, policy and eligibility operations | Define outcome and acceptance for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0500 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0502 | P09 — Operations and administration | Evidence, policy and eligibility operations | Trace controlling requirements — Evidence, policy and eligibility operations | Trace controlling requirements for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0501 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0503 | P09 — Operations and administration | Evidence, policy and eligibility operations | Audit the current implementation — Evidence, policy and eligibility operations | Audit the current implementation for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0502 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0504 | P09 — Operations and administration | Evidence, policy and eligibility operations | Write user stories and edge cases — Evidence, policy and eligibility operations | Write user stories and edge cases for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0503 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0505 | P09 — Operations and administration | Evidence, policy and eligibility operations | Model roles and permissions — Evidence, policy and eligibility operations | Model roles and permissions for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0504 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0506 | P09 — Operations and administration | Evidence, policy and eligibility operations | Design the data contract — Evidence, policy and eligibility operations | Design the data contract for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0505 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0507 | P09 — Operations and administration | Evidence, policy and eligibility operations | Define the state machine — Evidence, policy and eligibility operations | Define the state machine for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0506 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0508 | P09 — Operations and administration | Evidence, policy and eligibility operations | Define commands, queries and events — Evidence, policy and eligibility operations | Define commands, queries and events for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0507 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0509 | P09 — Operations and administration | Evidence, policy and eligibility operations | Map the complete UX flow — Evidence, policy and eligibility operations | Map the complete UX flow for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0508 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0510 | P09 — Operations and administration | Evidence, policy and eligibility operations | Create responsive wireframes — Evidence, policy and eligibility operations | Create responsive wireframes for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0509 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0511 | P09 — Operations and administration | Evidence, policy and eligibility operations | Complete high-fidelity design — Evidence, policy and eligibility operations | Complete high-fidelity design for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0510 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0512 | P09 — Operations and administration | Evidence, policy and eligibility operations | Specify accessibility behaviour — Evidence, policy and eligibility operations | Specify accessibility behaviour for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0511 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0513 | P09 — Operations and administration | Evidence, policy and eligibility operations | Implement schema and migrations — Evidence, policy and eligibility operations | Implement schema and migrations for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0512 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0514 | P09 — Operations and administration | Evidence, policy and eligibility operations | Implement server-side domain logic — Evidence, policy and eligibility operations | Implement server-side domain logic for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0513 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0515 | P09 — Operations and administration | Evidence, policy and eligibility operations | Implement the frontend foundation — Evidence, policy and eligibility operations | Implement the frontend foundation for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0514 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0516 | P09 — Operations and administration | Evidence, policy and eligibility operations | Implement the happy path — Evidence, policy and eligibility operations | Implement the happy path for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0515 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0517 | P09 — Operations and administration | Evidence, policy and eligibility operations | Implement non-happy states — Evidence, policy and eligibility operations | Implement non-happy states for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0516 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0518 | P09 — Operations and administration | Evidence, policy and eligibility operations | Add audit and observability — Evidence, policy and eligibility operations | Add audit and observability for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0517 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0519 | P09 — Operations and administration | Evidence, policy and eligibility operations | Apply security and privacy controls — Evidence, policy and eligibility operations | Apply security and privacy controls for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0518 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0520 | P09 — Operations and administration | Evidence, policy and eligibility operations | Write unit tests — Evidence, policy and eligibility operations | Write unit tests for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0519 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0521 | P09 — Operations and administration | Evidence, policy and eligibility operations | Write integration tests — Evidence, policy and eligibility operations | Write integration tests for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0520 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0522 | P09 — Operations and administration | Evidence, policy and eligibility operations | Write end-to-end tests — Evidence, policy and eligibility operations | Write end-to-end tests for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0521 | Operations Platform Lead | P0 | Development / preview | Yes | Not started
TASK-0523 | P09 — Operations and administration | Evidence, policy and eligibility operations | Validate performance and resilience — Evidence, policy and eligibility operations | Validate performance and resilience for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0522 | Operations Platform Lead | P0 | Development / preview | Yes | Not started
TASK-0524 | P09 — Operations and administration | Evidence, policy and eligibility operations | Publish operating documentation — Evidence, policy and eligibility operations | Publish operating documentation for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0523 | Operations Platform Lead | P0 | Development / preview | Yes | Not started
TASK-0525 | P09 — Operations and administration | Evidence, policy and eligibility operations | Pass preview acceptance — Evidence, policy and eligibility operations | Pass preview acceptance for Evidence, policy and eligibility operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Evidence, policy and eligibility operations: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0524 | Operations Platform Lead | P0 | Preview gate | Yes | Not started
TASK-0526 | P09 — Operations and administration | Risk, finance and approval operations | Define outcome and acceptance — Risk, finance and approval operations | Define outcome and acceptance for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0500 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0527 | P09 — Operations and administration | Risk, finance and approval operations | Trace controlling requirements — Risk, finance and approval operations | Trace controlling requirements for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0526 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0528 | P09 — Operations and administration | Risk, finance and approval operations | Audit the current implementation — Risk, finance and approval operations | Audit the current implementation for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0527 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0529 | P09 — Operations and administration | Risk, finance and approval operations | Write user stories and edge cases — Risk, finance and approval operations | Write user stories and edge cases for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0528 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0530 | P09 — Operations and administration | Risk, finance and approval operations | Model roles and permissions — Risk, finance and approval operations | Model roles and permissions for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0529 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0531 | P09 — Operations and administration | Risk, finance and approval operations | Design the data contract — Risk, finance and approval operations | Design the data contract for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0530 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0532 | P09 — Operations and administration | Risk, finance and approval operations | Define the state machine — Risk, finance and approval operations | Define the state machine for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0531 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0533 | P09 — Operations and administration | Risk, finance and approval operations | Define commands, queries and events — Risk, finance and approval operations | Define commands, queries and events for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0532 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0534 | P09 — Operations and administration | Risk, finance and approval operations | Map the complete UX flow — Risk, finance and approval operations | Map the complete UX flow for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0533 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0535 | P09 — Operations and administration | Risk, finance and approval operations | Create responsive wireframes — Risk, finance and approval operations | Create responsive wireframes for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0534 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0536 | P09 — Operations and administration | Risk, finance and approval operations | Complete high-fidelity design — Risk, finance and approval operations | Complete high-fidelity design for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0535 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0537 | P09 — Operations and administration | Risk, finance and approval operations | Specify accessibility behaviour — Risk, finance and approval operations | Specify accessibility behaviour for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0536 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0538 | P09 — Operations and administration | Risk, finance and approval operations | Implement schema and migrations — Risk, finance and approval operations | Implement schema and migrations for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0537 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0539 | P09 — Operations and administration | Risk, finance and approval operations | Implement server-side domain logic — Risk, finance and approval operations | Implement server-side domain logic for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0538 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0540 | P09 — Operations and administration | Risk, finance and approval operations | Implement the frontend foundation — Risk, finance and approval operations | Implement the frontend foundation for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0539 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0541 | P09 — Operations and administration | Risk, finance and approval operations | Implement the happy path — Risk, finance and approval operations | Implement the happy path for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0540 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0542 | P09 — Operations and administration | Risk, finance and approval operations | Implement non-happy states — Risk, finance and approval operations | Implement non-happy states for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0541 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0543 | P09 — Operations and administration | Risk, finance and approval operations | Add audit and observability — Risk, finance and approval operations | Add audit and observability for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0542 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0544 | P09 — Operations and administration | Risk, finance and approval operations | Apply security and privacy controls — Risk, finance and approval operations | Apply security and privacy controls for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0543 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0545 | P09 — Operations and administration | Risk, finance and approval operations | Write unit tests — Risk, finance and approval operations | Write unit tests for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0544 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0546 | P09 — Operations and administration | Risk, finance and approval operations | Write integration tests — Risk, finance and approval operations | Write integration tests for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0545 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0547 | P09 — Operations and administration | Risk, finance and approval operations | Write end-to-end tests — Risk, finance and approval operations | Write end-to-end tests for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0546 | Operations Platform Lead | P0 | Development / preview | Yes | Not started
TASK-0548 | P09 — Operations and administration | Risk, finance and approval operations | Validate performance and resilience — Risk, finance and approval operations | Validate performance and resilience for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0547 | Operations Platform Lead | P0 | Development / preview | Yes | Not started
TASK-0549 | P09 — Operations and administration | Risk, finance and approval operations | Publish operating documentation — Risk, finance and approval operations | Publish operating documentation for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0548 | Operations Platform Lead | P0 | Development / preview | Yes | Not started
TASK-0550 | P09 — Operations and administration | Risk, finance and approval operations | Pass preview acceptance — Risk, finance and approval operations | Pass preview acceptance for Risk, finance and approval operations. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Risk, finance and approval operations: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0549 | Operations Platform Lead | P0 | Preview gate | Yes | Not started
TASK-0551 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Define outcome and acceptance — Admin, audit, feature and emergency controls | Define outcome and acceptance for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0500 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0552 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Trace controlling requirements — Admin, audit, feature and emergency controls | Trace controlling requirements for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0551 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0553 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Audit the current implementation — Admin, audit, feature and emergency controls | Audit the current implementation for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0552 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0554 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Write user stories and edge cases — Admin, audit, feature and emergency controls | Write user stories and edge cases for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0553 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0555 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Model roles and permissions — Admin, audit, feature and emergency controls | Model roles and permissions for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0554 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0556 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Design the data contract — Admin, audit, feature and emergency controls | Design the data contract for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0555 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0557 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Define the state machine — Admin, audit, feature and emergency controls | Define the state machine for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0556 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0558 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Define commands, queries and events — Admin, audit, feature and emergency controls | Define commands, queries and events for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0557 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0559 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Map the complete UX flow — Admin, audit, feature and emergency controls | Map the complete UX flow for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0558 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0560 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Create responsive wireframes — Admin, audit, feature and emergency controls | Create responsive wireframes for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0559 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0561 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Complete high-fidelity design — Admin, audit, feature and emergency controls | Complete high-fidelity design for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0560 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0562 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Specify accessibility behaviour — Admin, audit, feature and emergency controls | Specify accessibility behaviour for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0561 | Operations Platform Lead | P1 | Local / design | No | Not started
TASK-0563 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Implement schema and migrations — Admin, audit, feature and emergency controls | Implement schema and migrations for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0562 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0564 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Implement server-side domain logic — Admin, audit, feature and emergency controls | Implement server-side domain logic for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0563 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0565 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Implement the frontend foundation — Admin, audit, feature and emergency controls | Implement the frontend foundation for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0564 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0566 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Implement the happy path — Admin, audit, feature and emergency controls | Implement the happy path for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0565 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0567 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Implement non-happy states — Admin, audit, feature and emergency controls | Implement non-happy states for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0566 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0568 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Add audit and observability — Admin, audit, feature and emergency controls | Add audit and observability for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0567 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0569 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Apply security and privacy controls — Admin, audit, feature and emergency controls | Apply security and privacy controls for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0568 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0570 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Write unit tests — Admin, audit, feature and emergency controls | Write unit tests for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0569 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0571 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Write integration tests — Admin, audit, feature and emergency controls | Write integration tests for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0570 | Operations Platform Lead | P1 | Development / preview | No | Not started
TASK-0572 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Write end-to-end tests — Admin, audit, feature and emergency controls | Write end-to-end tests for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0571 | Operations Platform Lead | P0 | Development / preview | Yes | Not started
TASK-0573 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Validate performance and resilience — Admin, audit, feature and emergency controls | Validate performance and resilience for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0572 | Operations Platform Lead | P0 | Development / preview | Yes | Not started
TASK-0574 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Publish operating documentation — Admin, audit, feature and emergency controls | Publish operating documentation for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0573 | Operations Platform Lead | P0 | Development / preview | Yes | Not started
TASK-0575 | P09 — Operations and administration | Admin, audit, feature and emergency controls | Pass preview acceptance — Admin, audit, feature and emergency controls | Pass preview acceptance for Admin, audit, feature and emergency controls. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Admin, audit, feature and emergency controls: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0574, TASK-0525, TASK-0550 | Operations Platform Lead | P0 | Preview gate | Yes | Not started
TASK-0576 | P10 — Buyer marketplace experience | Search results, filters, list and map | Define outcome and acceptance — Search results, filters, list and map | Define outcome and acceptance for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0575 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0577 | P10 — Buyer marketplace experience | Search results, filters, list and map | Trace controlling requirements — Search results, filters, list and map | Trace controlling requirements for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0576 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0578 | P10 — Buyer marketplace experience | Search results, filters, list and map | Audit the current implementation — Search results, filters, list and map | Audit the current implementation for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0577 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0579 | P10 — Buyer marketplace experience | Search results, filters, list and map | Write user stories and edge cases — Search results, filters, list and map | Write user stories and edge cases for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0578 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0580 | P10 — Buyer marketplace experience | Search results, filters, list and map | Model roles and permissions — Search results, filters, list and map | Model roles and permissions for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0579 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0581 | P10 — Buyer marketplace experience | Search results, filters, list and map | Design the data contract — Search results, filters, list and map | Design the data contract for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0580 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0582 | P10 — Buyer marketplace experience | Search results, filters, list and map | Define the state machine — Search results, filters, list and map | Define the state machine for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0581 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0583 | P10 — Buyer marketplace experience | Search results, filters, list and map | Define commands, queries and events — Search results, filters, list and map | Define commands, queries and events for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0582 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0584 | P10 — Buyer marketplace experience | Search results, filters, list and map | Map the complete UX flow — Search results, filters, list and map | Map the complete UX flow for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0583 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0585 | P10 — Buyer marketplace experience | Search results, filters, list and map | Create responsive wireframes — Search results, filters, list and map | Create responsive wireframes for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0584 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0586 | P10 — Buyer marketplace experience | Search results, filters, list and map | Complete high-fidelity design — Search results, filters, list and map | Complete high-fidelity design for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0585 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0587 | P10 — Buyer marketplace experience | Search results, filters, list and map | Specify accessibility behaviour — Search results, filters, list and map | Specify accessibility behaviour for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0586 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0588 | P10 — Buyer marketplace experience | Search results, filters, list and map | Implement schema and migrations — Search results, filters, list and map | Implement schema and migrations for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0587 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0589 | P10 — Buyer marketplace experience | Search results, filters, list and map | Implement server-side domain logic — Search results, filters, list and map | Implement server-side domain logic for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0588 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0590 | P10 — Buyer marketplace experience | Search results, filters, list and map | Implement the frontend foundation — Search results, filters, list and map | Implement the frontend foundation for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0589 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0591 | P10 — Buyer marketplace experience | Search results, filters, list and map | Implement the happy path — Search results, filters, list and map | Implement the happy path for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0590 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0592 | P10 — Buyer marketplace experience | Search results, filters, list and map | Implement non-happy states — Search results, filters, list and map | Implement non-happy states for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0591 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0593 | P10 — Buyer marketplace experience | Search results, filters, list and map | Add audit and observability — Search results, filters, list and map | Add audit and observability for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0592 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0594 | P10 — Buyer marketplace experience | Search results, filters, list and map | Apply security and privacy controls — Search results, filters, list and map | Apply security and privacy controls for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0593 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0595 | P10 — Buyer marketplace experience | Search results, filters, list and map | Write unit tests — Search results, filters, list and map | Write unit tests for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0594 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0596 | P10 — Buyer marketplace experience | Search results, filters, list and map | Write integration tests — Search results, filters, list and map | Write integration tests for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0595 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0597 | P10 — Buyer marketplace experience | Search results, filters, list and map | Write end-to-end tests — Search results, filters, list and map | Write end-to-end tests for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0596 | Buyer Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0598 | P10 — Buyer marketplace experience | Search results, filters, list and map | Validate performance and resilience — Search results, filters, list and map | Validate performance and resilience for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0597 | Buyer Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0599 | P10 — Buyer marketplace experience | Search results, filters, list and map | Publish operating documentation — Search results, filters, list and map | Publish operating documentation for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0598 | Buyer Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0600 | P10 — Buyer marketplace experience | Search results, filters, list and map | Pass preview acceptance — Search results, filters, list and map | Pass preview acceptance for Search results, filters, list and map. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Search results, filters, list and map: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0599 | Buyer Product Engineer | P0 | Preview gate | Yes | Not started
TASK-0601 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Define outcome and acceptance — Canonical property and exact listing detail | Define outcome and acceptance for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0575 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0602 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Trace controlling requirements — Canonical property and exact listing detail | Trace controlling requirements for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0601 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0603 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Audit the current implementation — Canonical property and exact listing detail | Audit the current implementation for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0602 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0604 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Write user stories and edge cases — Canonical property and exact listing detail | Write user stories and edge cases for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0603 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0605 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Model roles and permissions — Canonical property and exact listing detail | Model roles and permissions for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0604 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0606 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Design the data contract — Canonical property and exact listing detail | Design the data contract for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0605 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0607 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Define the state machine — Canonical property and exact listing detail | Define the state machine for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0606 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0608 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Define commands, queries and events — Canonical property and exact listing detail | Define commands, queries and events for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0607 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0609 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Map the complete UX flow — Canonical property and exact listing detail | Map the complete UX flow for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0608 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0610 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Create responsive wireframes — Canonical property and exact listing detail | Create responsive wireframes for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0609 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0611 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Complete high-fidelity design — Canonical property and exact listing detail | Complete high-fidelity design for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0610 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0612 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Specify accessibility behaviour — Canonical property and exact listing detail | Specify accessibility behaviour for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0611 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0613 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Implement schema and migrations — Canonical property and exact listing detail | Implement schema and migrations for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0612 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0614 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Implement server-side domain logic — Canonical property and exact listing detail | Implement server-side domain logic for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0613 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0615 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Implement the frontend foundation — Canonical property and exact listing detail | Implement the frontend foundation for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0614 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0616 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Implement the happy path — Canonical property and exact listing detail | Implement the happy path for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0615 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0617 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Implement non-happy states — Canonical property and exact listing detail | Implement non-happy states for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0616 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0618 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Add audit and observability — Canonical property and exact listing detail | Add audit and observability for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0617 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0619 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Apply security and privacy controls — Canonical property and exact listing detail | Apply security and privacy controls for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0618 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0620 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Write unit tests — Canonical property and exact listing detail | Write unit tests for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0619 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0621 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Write integration tests — Canonical property and exact listing detail | Write integration tests for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0620 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0622 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Write end-to-end tests — Canonical property and exact listing detail | Write end-to-end tests for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0621 | Buyer Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0623 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Validate performance and resilience — Canonical property and exact listing detail | Validate performance and resilience for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0622 | Buyer Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0624 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Publish operating documentation — Canonical property and exact listing detail | Publish operating documentation for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0623 | Buyer Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0625 | P10 — Buyer marketplace experience | Canonical property and exact listing detail | Pass preview acceptance — Canonical property and exact listing detail | Pass preview acceptance for Canonical property and exact listing detail. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Canonical property and exact listing detail: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0624 | Buyer Product Engineer | P0 | Preview gate | Yes | Not started
TASK-0626 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Define outcome and acceptance — Buyer account, saved stays and support | Define outcome and acceptance for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0575 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0627 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Trace controlling requirements — Buyer account, saved stays and support | Trace controlling requirements for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0626 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0628 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Audit the current implementation — Buyer account, saved stays and support | Audit the current implementation for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0627 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0629 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Write user stories and edge cases — Buyer account, saved stays and support | Write user stories and edge cases for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0628 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0630 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Model roles and permissions — Buyer account, saved stays and support | Model roles and permissions for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0629 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0631 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Design the data contract — Buyer account, saved stays and support | Design the data contract for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0630 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0632 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Define the state machine — Buyer account, saved stays and support | Define the state machine for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0631 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0633 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Define commands, queries and events — Buyer account, saved stays and support | Define commands, queries and events for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0632 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0634 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Map the complete UX flow — Buyer account, saved stays and support | Map the complete UX flow for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0633 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0635 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Create responsive wireframes — Buyer account, saved stays and support | Create responsive wireframes for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0634 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0636 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Complete high-fidelity design — Buyer account, saved stays and support | Complete high-fidelity design for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0635 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0637 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Specify accessibility behaviour — Buyer account, saved stays and support | Specify accessibility behaviour for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0636 | Buyer Product Engineer | P1 | Local / design | No | Not started
TASK-0638 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Implement schema and migrations — Buyer account, saved stays and support | Implement schema and migrations for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0637 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0639 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Implement server-side domain logic — Buyer account, saved stays and support | Implement server-side domain logic for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0638 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0640 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Implement the frontend foundation — Buyer account, saved stays and support | Implement the frontend foundation for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0639 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0641 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Implement the happy path — Buyer account, saved stays and support | Implement the happy path for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0640 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0642 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Implement non-happy states — Buyer account, saved stays and support | Implement non-happy states for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0641 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0643 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Add audit and observability — Buyer account, saved stays and support | Add audit and observability for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0642 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0644 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Apply security and privacy controls — Buyer account, saved stays and support | Apply security and privacy controls for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0643 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0645 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Write unit tests — Buyer account, saved stays and support | Write unit tests for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0644 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0646 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Write integration tests — Buyer account, saved stays and support | Write integration tests for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0645 | Buyer Product Engineer | P1 | Development / preview | No | Not started
TASK-0647 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Write end-to-end tests — Buyer account, saved stays and support | Write end-to-end tests for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0646 | Buyer Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0648 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Validate performance and resilience — Buyer account, saved stays and support | Validate performance and resilience for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0647 | Buyer Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0649 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Publish operating documentation — Buyer account, saved stays and support | Publish operating documentation for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0648 | Buyer Product Engineer | P0 | Development / preview | Yes | Not started
TASK-0650 | P10 — Buyer marketplace experience | Buyer account, saved stays and support | Pass preview acceptance — Buyer account, saved stays and support | Pass preview acceptance for Buyer account, saved stays and support. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Buyer account, saved stays and support: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0649, TASK-0600, TASK-0625 | Buyer Product Engineer | P0 | Preview gate | Yes | Not started
TASK-0651 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Define outcome and acceptance — Pricing, fees and versioned quotes | Define outcome and acceptance for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0650 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0652 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Trace controlling requirements — Pricing, fees and versioned quotes | Trace controlling requirements for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0651 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0653 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Audit the current implementation — Pricing, fees and versioned quotes | Audit the current implementation for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0652 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0654 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Write user stories and edge cases — Pricing, fees and versioned quotes | Write user stories and edge cases for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0653 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0655 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Model roles and permissions — Pricing, fees and versioned quotes | Model roles and permissions for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0654 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0656 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Design the data contract — Pricing, fees and versioned quotes | Design the data contract for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0655 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0657 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Define the state machine — Pricing, fees and versioned quotes | Define the state machine for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0656 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0658 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Define commands, queries and events — Pricing, fees and versioned quotes | Define commands, queries and events for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0657 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0659 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Map the complete UX flow — Pricing, fees and versioned quotes | Map the complete UX flow for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0658 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0660 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Create responsive wireframes — Pricing, fees and versioned quotes | Create responsive wireframes for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0659 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0661 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Complete high-fidelity design — Pricing, fees and versioned quotes | Complete high-fidelity design for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0660 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0662 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Specify accessibility behaviour — Pricing, fees and versioned quotes | Specify accessibility behaviour for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0661 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0663 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Implement schema and migrations — Pricing, fees and versioned quotes | Implement schema and migrations for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0662 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0664 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Implement server-side domain logic — Pricing, fees and versioned quotes | Implement server-side domain logic for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0663 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0665 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Implement the frontend foundation — Pricing, fees and versioned quotes | Implement the frontend foundation for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0664 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0666 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Implement the happy path — Pricing, fees and versioned quotes | Implement the happy path for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0665 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0667 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Implement non-happy states — Pricing, fees and versioned quotes | Implement non-happy states for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0666 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0668 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Add audit and observability — Pricing, fees and versioned quotes | Add audit and observability for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0667 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0669 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Apply security and privacy controls — Pricing, fees and versioned quotes | Apply security and privacy controls for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0668 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0670 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Write unit tests — Pricing, fees and versioned quotes | Write unit tests for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0669 | Marketplace Domain Lead | P0 | Development / preview | Yes | Not started
TASK-0671 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Write integration tests — Pricing, fees and versioned quotes | Write integration tests for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0670 | Marketplace Domain Lead | P0 | Development / preview | Yes | Not started
TASK-0672 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Write end-to-end tests — Pricing, fees and versioned quotes | Write end-to-end tests for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0671 | Marketplace Domain Lead | P0 | Development / preview | Yes | Not started
TASK-0673 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Validate performance and resilience — Pricing, fees and versioned quotes | Validate performance and resilience for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0672 | Marketplace Domain Lead | P0 | Development / preview | Yes | Not started
TASK-0674 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Publish operating documentation — Pricing, fees and versioned quotes | Publish operating documentation for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0673 | Marketplace Domain Lead | P0 | Development / preview | Yes | Not started
TASK-0675 | P11 — Pricing, listing and inventory state | Pricing, fees and versioned quotes | Pass preview acceptance — Pricing, fees and versioned quotes | Pass preview acceptance for Pricing, fees and versioned quotes. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pricing, fees and versioned quotes: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0674 | Marketplace Domain Lead | P0 | Preview gate | Yes | Not started
TASK-0676 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Define outcome and acceptance — Listing publication, realtime projection and inventory holds | Define outcome and acceptance for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0650 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0677 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Trace controlling requirements — Listing publication, realtime projection and inventory holds | Trace controlling requirements for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0676 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0678 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Audit the current implementation — Listing publication, realtime projection and inventory holds | Audit the current implementation for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0677 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0679 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Write user stories and edge cases — Listing publication, realtime projection and inventory holds | Write user stories and edge cases for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0678 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0680 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Model roles and permissions — Listing publication, realtime projection and inventory holds | Model roles and permissions for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0679 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0681 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Design the data contract — Listing publication, realtime projection and inventory holds | Design the data contract for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0680 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0682 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Define the state machine — Listing publication, realtime projection and inventory holds | Define the state machine for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0681 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0683 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Define commands, queries and events — Listing publication, realtime projection and inventory holds | Define commands, queries and events for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0682 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0684 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Map the complete UX flow — Listing publication, realtime projection and inventory holds | Map the complete UX flow for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0683 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0685 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Create responsive wireframes — Listing publication, realtime projection and inventory holds | Create responsive wireframes for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0684 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0686 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Complete high-fidelity design — Listing publication, realtime projection and inventory holds | Complete high-fidelity design for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0685 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0687 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Specify accessibility behaviour — Listing publication, realtime projection and inventory holds | Specify accessibility behaviour for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0686 | Marketplace Domain Lead | P1 | Local / design | No | Not started
TASK-0688 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Implement schema and migrations — Listing publication, realtime projection and inventory holds | Implement schema and migrations for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0687 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0689 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Implement server-side domain logic — Listing publication, realtime projection and inventory holds | Implement server-side domain logic for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0688 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0690 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Implement the frontend foundation — Listing publication, realtime projection and inventory holds | Implement the frontend foundation for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0689 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0691 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Implement the happy path — Listing publication, realtime projection and inventory holds | Implement the happy path for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0690 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0692 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Implement non-happy states — Listing publication, realtime projection and inventory holds | Implement non-happy states for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0691 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0693 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Add audit and observability — Listing publication, realtime projection and inventory holds | Add audit and observability for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0692 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0694 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Apply security and privacy controls — Listing publication, realtime projection and inventory holds | Apply security and privacy controls for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0693 | Marketplace Domain Lead | P1 | Development / preview | No | Not started
TASK-0695 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Write unit tests — Listing publication, realtime projection and inventory holds | Write unit tests for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0694 | Marketplace Domain Lead | P0 | Development / preview | Yes | Not started
TASK-0696 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Write integration tests — Listing publication, realtime projection and inventory holds | Write integration tests for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0695 | Marketplace Domain Lead | P0 | Development / preview | Yes | Not started
TASK-0697 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Write end-to-end tests — Listing publication, realtime projection and inventory holds | Write end-to-end tests for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0696 | Marketplace Domain Lead | P0 | Development / preview | Yes | Not started
TASK-0698 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Validate performance and resilience — Listing publication, realtime projection and inventory holds | Validate performance and resilience for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0697 | Marketplace Domain Lead | P0 | Development / preview | Yes | Not started
TASK-0699 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Publish operating documentation — Listing publication, realtime projection and inventory holds | Publish operating documentation for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0698 | Marketplace Domain Lead | P0 | Development / preview | Yes | Not started
TASK-0700 | P11 — Pricing, listing and inventory state | Listing publication, realtime projection and inventory holds | Pass preview acceptance — Listing publication, realtime projection and inventory holds | Pass preview acceptance for Listing publication, realtime projection and inventory holds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Listing publication, realtime projection and inventory holds: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0699, TASK-0675 | Marketplace Domain Lead | P0 | Preview gate | Yes | Not started
TASK-0701 | P12 — Checkout, payments and ledger | Checkout review and guest details | Define outcome and acceptance — Checkout review and guest details | Define outcome and acceptance for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0700 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0702 | P12 — Checkout, payments and ledger | Checkout review and guest details | Trace controlling requirements — Checkout review and guest details | Trace controlling requirements for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0701 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0703 | P12 — Checkout, payments and ledger | Checkout review and guest details | Audit the current implementation — Checkout review and guest details | Audit the current implementation for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0702 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0704 | P12 — Checkout, payments and ledger | Checkout review and guest details | Write user stories and edge cases — Checkout review and guest details | Write user stories and edge cases for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0703 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0705 | P12 — Checkout, payments and ledger | Checkout review and guest details | Model roles and permissions — Checkout review and guest details | Model roles and permissions for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0704 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0706 | P12 — Checkout, payments and ledger | Checkout review and guest details | Design the data contract — Checkout review and guest details | Design the data contract for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0705 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0707 | P12 — Checkout, payments and ledger | Checkout review and guest details | Define the state machine — Checkout review and guest details | Define the state machine for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0706 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0708 | P12 — Checkout, payments and ledger | Checkout review and guest details | Define commands, queries and events — Checkout review and guest details | Define commands, queries and events for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0707 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0709 | P12 — Checkout, payments and ledger | Checkout review and guest details | Map the complete UX flow — Checkout review and guest details | Map the complete UX flow for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0708 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0710 | P12 — Checkout, payments and ledger | Checkout review and guest details | Create responsive wireframes — Checkout review and guest details | Create responsive wireframes for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0709 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0711 | P12 — Checkout, payments and ledger | Checkout review and guest details | Complete high-fidelity design — Checkout review and guest details | Complete high-fidelity design for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0710 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0712 | P12 — Checkout, payments and ledger | Checkout review and guest details | Specify accessibility behaviour — Checkout review and guest details | Specify accessibility behaviour for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0711 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0713 | P12 — Checkout, payments and ledger | Checkout review and guest details | Implement schema and migrations — Checkout review and guest details | Implement schema and migrations for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0712 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0714 | P12 — Checkout, payments and ledger | Checkout review and guest details | Implement server-side domain logic — Checkout review and guest details | Implement server-side domain logic for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0713 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0715 | P12 — Checkout, payments and ledger | Checkout review and guest details | Implement the frontend foundation — Checkout review and guest details | Implement the frontend foundation for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0714 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0716 | P12 — Checkout, payments and ledger | Checkout review and guest details | Implement the happy path — Checkout review and guest details | Implement the happy path for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0715 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0717 | P12 — Checkout, payments and ledger | Checkout review and guest details | Implement non-happy states — Checkout review and guest details | Implement non-happy states for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0716 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0718 | P12 — Checkout, payments and ledger | Checkout review and guest details | Add audit and observability — Checkout review and guest details | Add audit and observability for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0717 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0719 | P12 — Checkout, payments and ledger | Checkout review and guest details | Apply security and privacy controls — Checkout review and guest details | Apply security and privacy controls for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0718 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0720 | P12 — Checkout, payments and ledger | Checkout review and guest details | Write unit tests — Checkout review and guest details | Write unit tests for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0719 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0721 | P12 — Checkout, payments and ledger | Checkout review and guest details | Write integration tests — Checkout review and guest details | Write integration tests for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0720 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0722 | P12 — Checkout, payments and ledger | Checkout review and guest details | Write end-to-end tests — Checkout review and guest details | Write end-to-end tests for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0721 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0723 | P12 — Checkout, payments and ledger | Checkout review and guest details | Validate performance and resilience — Checkout review and guest details | Validate performance and resilience for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0722 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0724 | P12 — Checkout, payments and ledger | Checkout review and guest details | Publish operating documentation — Checkout review and guest details | Publish operating documentation for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0723 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0725 | P12 — Checkout, payments and ledger | Checkout review and guest details | Pass preview acceptance — Checkout review and guest details | Pass preview acceptance for Checkout review and guest details. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Checkout review and guest details: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0724 | Payments Engineering Lead | P0 | Preview gate | Yes | Not started
TASK-0726 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Define outcome and acceptance — Payment adapter, webhooks and uncertain states | Define outcome and acceptance for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0700 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0727 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Trace controlling requirements — Payment adapter, webhooks and uncertain states | Trace controlling requirements for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0726 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0728 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Audit the current implementation — Payment adapter, webhooks and uncertain states | Audit the current implementation for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0727 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0729 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Write user stories and edge cases — Payment adapter, webhooks and uncertain states | Write user stories and edge cases for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0728 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0730 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Model roles and permissions — Payment adapter, webhooks and uncertain states | Model roles and permissions for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0729 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0731 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Design the data contract — Payment adapter, webhooks and uncertain states | Design the data contract for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0730 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0732 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Define the state machine — Payment adapter, webhooks and uncertain states | Define the state machine for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0731 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0733 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Define commands, queries and events — Payment adapter, webhooks and uncertain states | Define commands, queries and events for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0732 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0734 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Map the complete UX flow — Payment adapter, webhooks and uncertain states | Map the complete UX flow for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0733 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0735 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Create responsive wireframes — Payment adapter, webhooks and uncertain states | Create responsive wireframes for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0734 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0736 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Complete high-fidelity design — Payment adapter, webhooks and uncertain states | Complete high-fidelity design for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0735 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0737 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Specify accessibility behaviour — Payment adapter, webhooks and uncertain states | Specify accessibility behaviour for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0736 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0738 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Implement schema and migrations — Payment adapter, webhooks and uncertain states | Implement schema and migrations for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0737 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0739 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Implement server-side domain logic — Payment adapter, webhooks and uncertain states | Implement server-side domain logic for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0738 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0740 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Implement the frontend foundation — Payment adapter, webhooks and uncertain states | Implement the frontend foundation for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0739 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0741 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Implement the happy path — Payment adapter, webhooks and uncertain states | Implement the happy path for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0740 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0742 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Implement non-happy states — Payment adapter, webhooks and uncertain states | Implement non-happy states for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0741 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0743 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Add audit and observability — Payment adapter, webhooks and uncertain states | Add audit and observability for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0742 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0744 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Apply security and privacy controls — Payment adapter, webhooks and uncertain states | Apply security and privacy controls for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0743 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0745 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Write unit tests — Payment adapter, webhooks and uncertain states | Write unit tests for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0744 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0746 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Write integration tests — Payment adapter, webhooks and uncertain states | Write integration tests for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0745 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0747 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Write end-to-end tests — Payment adapter, webhooks and uncertain states | Write end-to-end tests for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0746 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0748 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Validate performance and resilience — Payment adapter, webhooks and uncertain states | Validate performance and resilience for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0747 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0749 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Publish operating documentation — Payment adapter, webhooks and uncertain states | Publish operating documentation for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0748 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0750 | P12 — Checkout, payments and ledger | Payment adapter, webhooks and uncertain states | Pass preview acceptance — Payment adapter, webhooks and uncertain states | Pass preview acceptance for Payment adapter, webhooks and uncertain states. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Payment adapter, webhooks and uncertain states: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0749 | Payments Engineering Lead | P0 | Preview gate | Yes | Not started
TASK-0751 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Define outcome and acceptance — Immutable ledger, refunds and reconciliation | Define outcome and acceptance for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0700 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0752 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Trace controlling requirements — Immutable ledger, refunds and reconciliation | Trace controlling requirements for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0751 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0753 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Audit the current implementation — Immutable ledger, refunds and reconciliation | Audit the current implementation for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0752 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0754 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Write user stories and edge cases — Immutable ledger, refunds and reconciliation | Write user stories and edge cases for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0753 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0755 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Model roles and permissions — Immutable ledger, refunds and reconciliation | Model roles and permissions for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0754 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0756 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Design the data contract — Immutable ledger, refunds and reconciliation | Design the data contract for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0755 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0757 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Define the state machine — Immutable ledger, refunds and reconciliation | Define the state machine for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0756 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0758 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Define commands, queries and events — Immutable ledger, refunds and reconciliation | Define commands, queries and events for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0757 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0759 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Map the complete UX flow — Immutable ledger, refunds and reconciliation | Map the complete UX flow for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0758 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0760 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Create responsive wireframes — Immutable ledger, refunds and reconciliation | Create responsive wireframes for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0759 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0761 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Complete high-fidelity design — Immutable ledger, refunds and reconciliation | Complete high-fidelity design for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0760 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0762 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Specify accessibility behaviour — Immutable ledger, refunds and reconciliation | Specify accessibility behaviour for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0761 | Payments Engineering Lead | P1 | Local / design | No | Not started
TASK-0763 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Implement schema and migrations — Immutable ledger, refunds and reconciliation | Implement schema and migrations for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0762 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0764 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Implement server-side domain logic — Immutable ledger, refunds and reconciliation | Implement server-side domain logic for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0763 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0765 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Implement the frontend foundation — Immutable ledger, refunds and reconciliation | Implement the frontend foundation for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0764 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0766 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Implement the happy path — Immutable ledger, refunds and reconciliation | Implement the happy path for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0765 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0767 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Implement non-happy states — Immutable ledger, refunds and reconciliation | Implement non-happy states for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0766 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0768 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Add audit and observability — Immutable ledger, refunds and reconciliation | Add audit and observability for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0767 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0769 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Apply security and privacy controls — Immutable ledger, refunds and reconciliation | Apply security and privacy controls for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0768 | Payments Engineering Lead | P1 | Development / preview | No | Not started
TASK-0770 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Write unit tests — Immutable ledger, refunds and reconciliation | Write unit tests for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0769 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0771 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Write integration tests — Immutable ledger, refunds and reconciliation | Write integration tests for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0770 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0772 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Write end-to-end tests — Immutable ledger, refunds and reconciliation | Write end-to-end tests for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0771 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0773 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Validate performance and resilience — Immutable ledger, refunds and reconciliation | Validate performance and resilience for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0772 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0774 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Publish operating documentation — Immutable ledger, refunds and reconciliation | Publish operating documentation for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0773 | Payments Engineering Lead | P0 | Development / preview | Yes | Not started
TASK-0775 | P12 — Checkout, payments and ledger | Immutable ledger, refunds and reconciliation | Pass preview acceptance — Immutable ledger, refunds and reconciliation | Pass preview acceptance for Immutable ledger, refunds and reconciliation. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Immutable ledger, refunds and reconciliation: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0774, TASK-0725, TASK-0750 | Payments Engineering Lead | P0 | Preview gate | Yes | Not started
TASK-0776 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Define outcome and acceptance — Transfer case and Reservation Passport | Define outcome and acceptance for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0775 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0777 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Trace controlling requirements — Transfer case and Reservation Passport | Trace controlling requirements for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0776 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0778 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Audit the current implementation — Transfer case and Reservation Passport | Audit the current implementation for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0777 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0779 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Write user stories and edge cases — Transfer case and Reservation Passport | Write user stories and edge cases for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0778 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0780 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Model roles and permissions — Transfer case and Reservation Passport | Model roles and permissions for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0779 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0781 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Design the data contract — Transfer case and Reservation Passport | Design the data contract for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0780 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0782 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Define the state machine — Transfer case and Reservation Passport | Define the state machine for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0781 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0783 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Define commands, queries and events — Transfer case and Reservation Passport | Define commands, queries and events for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0782 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0784 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Map the complete UX flow — Transfer case and Reservation Passport | Map the complete UX flow for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0783 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0785 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Create responsive wireframes — Transfer case and Reservation Passport | Create responsive wireframes for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0784 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0786 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Complete high-fidelity design — Transfer case and Reservation Passport | Complete high-fidelity design for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0785 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0787 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Specify accessibility behaviour — Transfer case and Reservation Passport | Specify accessibility behaviour for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0786 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0788 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Implement schema and migrations — Transfer case and Reservation Passport | Implement schema and migrations for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0787 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0789 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Implement server-side domain logic — Transfer case and Reservation Passport | Implement server-side domain logic for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0788 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0790 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Implement the frontend foundation — Transfer case and Reservation Passport | Implement the frontend foundation for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0789 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0791 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Implement the happy path — Transfer case and Reservation Passport | Implement the happy path for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0790 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0792 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Implement non-happy states — Transfer case and Reservation Passport | Implement non-happy states for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0791 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0793 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Add audit and observability — Transfer case and Reservation Passport | Add audit and observability for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0792 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0794 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Apply security and privacy controls — Transfer case and Reservation Passport | Apply security and privacy controls for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0793 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0795 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Write unit tests — Transfer case and Reservation Passport | Write unit tests for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0794 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0796 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Write integration tests — Transfer case and Reservation Passport | Write integration tests for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0795 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0797 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Write end-to-end tests — Transfer case and Reservation Passport | Write end-to-end tests for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0796 | Fulfilment Product Lead | P0 | Development / preview | Yes | Not started
TASK-0798 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Validate performance and resilience — Transfer case and Reservation Passport | Validate performance and resilience for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0797 | Fulfilment Product Lead | P0 | Development / preview | Yes | Not started
TASK-0799 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Publish operating documentation — Transfer case and Reservation Passport | Publish operating documentation for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0798 | Fulfilment Product Lead | P0 | Development / preview | Yes | Not started
TASK-0800 | P13 — Transfer, Passport and arrival | Transfer case and Reservation Passport | Pass preview acceptance — Transfer case and Reservation Passport | Pass preview acceptance for Transfer case and Reservation Passport. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Transfer case and Reservation Passport: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0799 | Fulfilment Product Lead | P0 | Preview gate | Yes | Not started
TASK-0801 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Define outcome and acceptance — Pre-arrival, address release and check-in outcome | Define outcome and acceptance for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0775 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0802 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Trace controlling requirements — Pre-arrival, address release and check-in outcome | Trace controlling requirements for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0801 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0803 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Audit the current implementation — Pre-arrival, address release and check-in outcome | Audit the current implementation for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0802 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0804 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Write user stories and edge cases — Pre-arrival, address release and check-in outcome | Write user stories and edge cases for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0803 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0805 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Model roles and permissions — Pre-arrival, address release and check-in outcome | Model roles and permissions for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0804 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0806 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Design the data contract — Pre-arrival, address release and check-in outcome | Design the data contract for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0805 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0807 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Define the state machine — Pre-arrival, address release and check-in outcome | Define the state machine for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0806 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0808 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Define commands, queries and events — Pre-arrival, address release and check-in outcome | Define commands, queries and events for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0807 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0809 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Map the complete UX flow — Pre-arrival, address release and check-in outcome | Map the complete UX flow for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0808 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0810 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Create responsive wireframes — Pre-arrival, address release and check-in outcome | Create responsive wireframes for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0809 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0811 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Complete high-fidelity design — Pre-arrival, address release and check-in outcome | Complete high-fidelity design for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0810 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0812 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Specify accessibility behaviour — Pre-arrival, address release and check-in outcome | Specify accessibility behaviour for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0811 | Fulfilment Product Lead | P1 | Local / design | No | Not started
TASK-0813 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Implement schema and migrations — Pre-arrival, address release and check-in outcome | Implement schema and migrations for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0812 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0814 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Implement server-side domain logic — Pre-arrival, address release and check-in outcome | Implement server-side domain logic for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0813 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0815 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Implement the frontend foundation — Pre-arrival, address release and check-in outcome | Implement the frontend foundation for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0814 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0816 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Implement the happy path — Pre-arrival, address release and check-in outcome | Implement the happy path for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0815 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0817 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Implement non-happy states — Pre-arrival, address release and check-in outcome | Implement non-happy states for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0816 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0818 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Add audit and observability — Pre-arrival, address release and check-in outcome | Add audit and observability for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0817 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0819 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Apply security and privacy controls — Pre-arrival, address release and check-in outcome | Apply security and privacy controls for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0818 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0820 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Write unit tests — Pre-arrival, address release and check-in outcome | Write unit tests for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0819 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0821 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Write integration tests — Pre-arrival, address release and check-in outcome | Write integration tests for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0820 | Fulfilment Product Lead | P1 | Development / preview | No | Not started
TASK-0822 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Write end-to-end tests — Pre-arrival, address release and check-in outcome | Write end-to-end tests for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0821 | Fulfilment Product Lead | P0 | Development / preview | Yes | Not started
TASK-0823 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Validate performance and resilience — Pre-arrival, address release and check-in outcome | Validate performance and resilience for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0822 | Fulfilment Product Lead | P0 | Development / preview | Yes | Not started
TASK-0824 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Publish operating documentation — Pre-arrival, address release and check-in outcome | Publish operating documentation for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0823 | Fulfilment Product Lead | P0 | Development / preview | Yes | Not started
TASK-0825 | P13 — Transfer, Passport and arrival | Pre-arrival, address release and check-in outcome | Pass preview acceptance — Pre-arrival, address release and check-in outcome | Pass preview acceptance for Pre-arrival, address release and check-in outcome. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Pre-arrival, address release and check-in outcome: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0824, TASK-0800 | Fulfilment Product Lead | P0 | Preview gate | Yes | Not started
TASK-0826 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Define outcome and acceptance — Claims, decisions and buyer refunds | Define outcome and acceptance for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0825 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0827 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Trace controlling requirements — Claims, decisions and buyer refunds | Trace controlling requirements for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0826 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0828 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Audit the current implementation — Claims, decisions and buyer refunds | Audit the current implementation for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0827 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0829 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Write user stories and edge cases — Claims, decisions and buyer refunds | Write user stories and edge cases for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0828 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0830 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Model roles and permissions — Claims, decisions and buyer refunds | Model roles and permissions for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0829 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0831 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Design the data contract — Claims, decisions and buyer refunds | Design the data contract for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0830 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0832 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Define the state machine — Claims, decisions and buyer refunds | Define the state machine for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0831 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0833 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Define commands, queries and events — Claims, decisions and buyer refunds | Define commands, queries and events for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0832 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0834 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Map the complete UX flow — Claims, decisions and buyer refunds | Map the complete UX flow for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0833 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0835 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Create responsive wireframes — Claims, decisions and buyer refunds | Create responsive wireframes for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0834 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0836 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Complete high-fidelity design — Claims, decisions and buyer refunds | Complete high-fidelity design for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0835 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0837 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Specify accessibility behaviour — Claims, decisions and buyer refunds | Specify accessibility behaviour for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0836 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0838 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Implement schema and migrations — Claims, decisions and buyer refunds | Implement schema and migrations for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0837 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0839 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Implement server-side domain logic — Claims, decisions and buyer refunds | Implement server-side domain logic for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0838 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0840 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Implement the frontend foundation — Claims, decisions and buyer refunds | Implement the frontend foundation for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0839 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0841 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Implement the happy path — Claims, decisions and buyer refunds | Implement the happy path for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0840 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0842 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Implement non-happy states — Claims, decisions and buyer refunds | Implement non-happy states for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0841 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0843 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Add audit and observability — Claims, decisions and buyer refunds | Add audit and observability for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0842 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0844 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Apply security and privacy controls — Claims, decisions and buyer refunds | Apply security and privacy controls for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0843 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0845 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Write unit tests — Claims, decisions and buyer refunds | Write unit tests for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0844 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0846 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Write integration tests — Claims, decisions and buyer refunds | Write integration tests for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0845 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0847 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Write end-to-end tests — Claims, decisions and buyer refunds | Write end-to-end tests for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0846 | Risk Operations Lead | P0 | Development / preview | Yes | Not started
TASK-0848 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Validate performance and resilience — Claims, decisions and buyer refunds | Validate performance and resilience for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0847 | Risk Operations Lead | P0 | Development / preview | Yes | Not started
TASK-0849 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Publish operating documentation — Claims, decisions and buyer refunds | Publish operating documentation for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0848 | Risk Operations Lead | P0 | Development / preview | Yes | Not started
TASK-0850 | P14 — Claims, recovery and seller payout | Claims, decisions and buyer refunds | Pass preview acceptance — Claims, decisions and buyer refunds | Pass preview acceptance for Claims, decisions and buyer refunds. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Claims, decisions and buyer refunds: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0849 | Risk Operations Lead | P0 | Preview gate | Yes | Not started
TASK-0851 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Define outcome and acceptance — Recovery, reserves and seller payouts | Define outcome and acceptance for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0825 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0852 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Trace controlling requirements — Recovery, reserves and seller payouts | Trace controlling requirements for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0851 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0853 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Audit the current implementation — Recovery, reserves and seller payouts | Audit the current implementation for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0852 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0854 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Write user stories and edge cases — Recovery, reserves and seller payouts | Write user stories and edge cases for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0853 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0855 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Model roles and permissions — Recovery, reserves and seller payouts | Model roles and permissions for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0854 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0856 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Design the data contract — Recovery, reserves and seller payouts | Design the data contract for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0855 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0857 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Define the state machine — Recovery, reserves and seller payouts | Define the state machine for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0856 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0858 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Define commands, queries and events — Recovery, reserves and seller payouts | Define commands, queries and events for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0857 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0859 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Map the complete UX flow — Recovery, reserves and seller payouts | Map the complete UX flow for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0858 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0860 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Create responsive wireframes — Recovery, reserves and seller payouts | Create responsive wireframes for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0859 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0861 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Complete high-fidelity design — Recovery, reserves and seller payouts | Complete high-fidelity design for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0860 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0862 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Specify accessibility behaviour — Recovery, reserves and seller payouts | Specify accessibility behaviour for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0861 | Risk Operations Lead | P1 | Local / design | No | Not started
TASK-0863 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Implement schema and migrations — Recovery, reserves and seller payouts | Implement schema and migrations for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0862 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0864 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Implement server-side domain logic — Recovery, reserves and seller payouts | Implement server-side domain logic for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0863 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0865 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Implement the frontend foundation — Recovery, reserves and seller payouts | Implement the frontend foundation for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0864 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0866 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Implement the happy path — Recovery, reserves and seller payouts | Implement the happy path for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0865 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0867 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Implement non-happy states — Recovery, reserves and seller payouts | Implement non-happy states for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0866 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0868 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Add audit and observability — Recovery, reserves and seller payouts | Add audit and observability for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0867 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0869 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Apply security and privacy controls — Recovery, reserves and seller payouts | Apply security and privacy controls for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0868 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0870 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Write unit tests — Recovery, reserves and seller payouts | Write unit tests for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0869 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0871 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Write integration tests — Recovery, reserves and seller payouts | Write integration tests for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: integration test suite | Database, API, provider adapter and authorization boundaries are exercised. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0870 | Risk Operations Lead | P1 | Development / preview | No | Not started
TASK-0872 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Write end-to-end tests — Recovery, reserves and seller payouts | Write end-to-end tests for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: browser end-to-end coverage | The complete user and operations flow passes with deterministic test data. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0871 | Risk Operations Lead | P0 | Development / preview | Yes | Not started
TASK-0873 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Validate performance and resilience — Recovery, reserves and seller payouts | Validate performance and resilience for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: performance and failure report | Budgets, concurrency, retries, reconnects and dependency failures meet targets. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0872 | Risk Operations Lead | P0 | Development / preview | Yes | Not started
TASK-0874 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Publish operating documentation — Recovery, reserves and seller payouts | Publish operating documentation for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: runbook and handoff | Owners can deploy, monitor, support, roll back and continue the module. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0873 | Risk Operations Lead | P0 | Development / preview | Yes | Not started
TASK-0875 | P14 — Claims, recovery and seller payout | Recovery, reserves and seller payouts | Pass preview acceptance — Recovery, reserves and seller payouts | Pass preview acceptance for Recovery, reserves and seller payouts. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Recovery, reserves and seller payouts: signed preview evidence | Product, design, engineering, security and operations acceptance evidence is linked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0874, TASK-0850 | Risk Operations Lead | P0 | Preview gate | Yes | Not started
TASK-0876 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Define outcome and acceptance — HubSpot, email, SMS and notification integration | Define outcome and acceptance for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0875 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0877 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Trace controlling requirements — HubSpot, email, SMS and notification integration | Trace controlling requirements for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0876 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0878 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Audit the current implementation — HubSpot, email, SMS and notification integration | Audit the current implementation for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0877 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0879 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Write user stories and edge cases — HubSpot, email, SMS and notification integration | Write user stories and edge cases for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0878 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0880 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Model roles and permissions — HubSpot, email, SMS and notification integration | Model roles and permissions for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0879 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0881 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Design the data contract — HubSpot, email, SMS and notification integration | Design the data contract for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0880 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0882 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Define the state machine — HubSpot, email, SMS and notification integration | Define the state machine for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0881 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0883 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Define commands, queries and events — HubSpot, email, SMS and notification integration | Define commands, queries and events for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0882 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0884 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Map the complete UX flow — HubSpot, email, SMS and notification integration | Map the complete UX flow for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0883 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0885 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Create responsive wireframes — HubSpot, email, SMS and notification integration | Create responsive wireframes for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0884 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0886 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Complete high-fidelity design — HubSpot, email, SMS and notification integration | Complete high-fidelity design for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0885 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0887 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Specify accessibility behaviour — HubSpot, email, SMS and notification integration | Specify accessibility behaviour for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0886 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0888 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Implement schema and migrations — HubSpot, email, SMS and notification integration | Implement schema and migrations for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0887 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0889 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Implement server-side domain logic — HubSpot, email, SMS and notification integration | Implement server-side domain logic for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0888 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0890 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Implement the frontend foundation — HubSpot, email, SMS and notification integration | Implement the frontend foundation for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0889 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0891 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Implement the happy path — HubSpot, email, SMS and notification integration | Implement the happy path for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0890 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0892 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Implement non-happy states — HubSpot, email, SMS and notification integration | Implement non-happy states for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0891 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0893 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Add audit and observability — HubSpot, email, SMS and notification integration | Add audit and observability for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0892 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0894 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Apply security and privacy controls — HubSpot, email, SMS and notification integration | Apply security and privacy controls for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0893 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0895 | P15 — CRM, notifications and responsible intelligence | HubSpot, email, SMS and notification integration | Write unit tests — HubSpot, email, SMS and notification integration | Write unit tests for HubSpot, email, SMS and notification integration. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | HubSpot, email, SMS and notification integration: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0894 | Integrations Lead | P1 | Development / preview | Yes | Not started
TASK-0896 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Define outcome and acceptance — AI assistance, analytics and privacy-safe search | Define outcome and acceptance for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0875 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0897 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Trace controlling requirements — AI assistance, analytics and privacy-safe search | Trace controlling requirements for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0896 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0898 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Audit the current implementation — AI assistance, analytics and privacy-safe search | Audit the current implementation for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0897 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0899 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Write user stories and edge cases — AI assistance, analytics and privacy-safe search | Write user stories and edge cases for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0898 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0900 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Model roles and permissions — AI assistance, analytics and privacy-safe search | Model roles and permissions for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0899 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0901 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Design the data contract — AI assistance, analytics and privacy-safe search | Design the data contract for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0900 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0902 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Define the state machine — AI assistance, analytics and privacy-safe search | Define the state machine for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0901 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0903 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Define commands, queries and events — AI assistance, analytics and privacy-safe search | Define commands, queries and events for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0902 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0904 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Map the complete UX flow — AI assistance, analytics and privacy-safe search | Map the complete UX flow for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0903 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0905 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Create responsive wireframes — AI assistance, analytics and privacy-safe search | Create responsive wireframes for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0904 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0906 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Complete high-fidelity design — AI assistance, analytics and privacy-safe search | Complete high-fidelity design for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0905 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0907 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Specify accessibility behaviour — AI assistance, analytics and privacy-safe search | Specify accessibility behaviour for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0906 | Integrations Lead | P1 | Local / design | No | Not started
TASK-0908 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Implement schema and migrations — AI assistance, analytics and privacy-safe search | Implement schema and migrations for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0907 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0909 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Implement server-side domain logic — AI assistance, analytics and privacy-safe search | Implement server-side domain logic for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0908 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0910 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Implement the frontend foundation — AI assistance, analytics and privacy-safe search | Implement the frontend foundation for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0909 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0911 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Implement the happy path — AI assistance, analytics and privacy-safe search | Implement the happy path for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0910 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0912 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Implement non-happy states — AI assistance, analytics and privacy-safe search | Implement non-happy states for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0911 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0913 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Add audit and observability — AI assistance, analytics and privacy-safe search | Add audit and observability for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0912 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0914 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Apply security and privacy controls — AI assistance, analytics and privacy-safe search | Apply security and privacy controls for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0913 | Integrations Lead | P1 | Development / preview | No | Not started
TASK-0915 | P15 — CRM, notifications and responsible intelligence | AI assistance, analytics and privacy-safe search | Write unit tests — AI assistance, analytics and privacy-safe search | Write unit tests for AI assistance, analytics and privacy-safe search. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | AI assistance, analytics and privacy-safe search: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0914, TASK-0895 | Integrations Lead | P1 | Development / preview | Yes | Not started
TASK-0916 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Define outcome and acceptance — Security, privacy and data governance hardening | Define outcome and acceptance for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0915 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0917 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Trace controlling requirements — Security, privacy and data governance hardening | Trace controlling requirements for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0916 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0918 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Audit the current implementation — Security, privacy and data governance hardening | Audit the current implementation for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0917 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0919 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Write user stories and edge cases — Security, privacy and data governance hardening | Write user stories and edge cases for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0918 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0920 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Model roles and permissions — Security, privacy and data governance hardening | Model roles and permissions for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0919 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0921 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Design the data contract — Security, privacy and data governance hardening | Design the data contract for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0920 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0922 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Define the state machine — Security, privacy and data governance hardening | Define the state machine for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0921 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0923 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Define commands, queries and events — Security, privacy and data governance hardening | Define commands, queries and events for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0922 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0924 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Map the complete UX flow — Security, privacy and data governance hardening | Map the complete UX flow for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0923 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0925 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Create responsive wireframes — Security, privacy and data governance hardening | Create responsive wireframes for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0924 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0926 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Complete high-fidelity design — Security, privacy and data governance hardening | Complete high-fidelity design for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0925 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0927 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Specify accessibility behaviour — Security, privacy and data governance hardening | Specify accessibility behaviour for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0926 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0928 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Implement schema and migrations — Security, privacy and data governance hardening | Implement schema and migrations for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0927 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0929 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Implement server-side domain logic — Security, privacy and data governance hardening | Implement server-side domain logic for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0928 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0930 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Implement the frontend foundation — Security, privacy and data governance hardening | Implement the frontend foundation for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0929 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0931 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Implement the happy path — Security, privacy and data governance hardening | Implement the happy path for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0930 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0932 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Implement non-happy states — Security, privacy and data governance hardening | Implement non-happy states for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0931 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0933 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Add audit and observability — Security, privacy and data governance hardening | Add audit and observability for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0932 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0934 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Apply security and privacy controls — Security, privacy and data governance hardening | Apply security and privacy controls for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0933 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0935 | P16 — Security, privacy, accessibility and reliability | Security, privacy and data governance hardening | Write unit tests — Security, privacy and data governance hardening | Write unit tests for Security, privacy and data governance hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Security, privacy and data governance hardening: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0934 | Quality and Security Lead | P0 | Development / preview | Yes | Not started
TASK-0936 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Define outcome and acceptance — Accessibility, performance and reliability hardening | Define outcome and acceptance for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: approved scope and measurable acceptance criteria | The outcome, exclusions, users and measurable completion evidence are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0915 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0937 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Trace controlling requirements — Accessibility, performance and reliability hardening | Trace controlling requirements for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: source-to-requirement trace | Every material requirement links to the current canonical source and conflict status. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0936 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0938 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Audit the current implementation — Accessibility, performance and reliability hardening | Audit the current implementation for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: current-state gap record | Implemented, partial, missing and misleading behaviour are demonstrated with evidence. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0937 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0939 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Write user stories and edge cases — Accessibility, performance and reliability hardening | Write user stories and edge cases for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: prioritized user stories | Happy paths, failures, recovery and abuse cases are covered. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0938 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0940 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Model roles and permissions — Accessibility, performance and reliability hardening | Model roles and permissions for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: authorization matrix | Every action has a server-enforced actor, scope and denial rule. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0939 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0941 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Design the data contract — Accessibility, performance and reliability hardening | Design the data contract for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: versioned data model | Identifiers, ownership, provenance, retention and constraints are defined. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0940 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0942 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Define the state machine — Accessibility, performance and reliability hardening | Define the state machine for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: state and transition specification | Allowed transitions, guards, invalidation and terminal states are unambiguous. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0941 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0943 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Define commands, queries and events — Accessibility, performance and reliability hardening | Define commands, queries and events for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: API and event contract | Idempotency, errors, versions and audit effects are specified. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0942 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0944 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Map the complete UX flow — Accessibility, performance and reliability hardening | Map the complete UX flow for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: screen and interaction flow | Entry, continuation, back navigation and recovery preserve user context. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0943 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0945 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Create responsive wireframes — Accessibility, performance and reliability hardening | Create responsive wireframes for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: responsive wireframes | Mobile, tablet, desktop and long-content behaviour are represented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0944 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0946 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Complete high-fidelity design — Accessibility, performance and reliability hardening | Complete high-fidelity design for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: approved high-fidelity design | Components, hierarchy, copy, imagery and states follow the design system. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0945 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0947 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Specify accessibility behaviour — Accessibility, performance and reliability hardening | Specify accessibility behaviour for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: accessibility contract | Keyboard, focus, semantics, announcements, contrast and reflow are testable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0946 | Quality and Security Lead | P1 | Local / design | No | Not started
TASK-0948 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Implement schema and migrations — Accessibility, performance and reliability hardening | Implement schema and migrations for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: reviewed migration and generated types | A clean non-production database applies the migration with constraints intact. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0947 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0949 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Implement server-side domain logic — Accessibility, performance and reliability hardening | Implement server-side domain logic for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: authoritative command and query handlers | Server checks current version, permission, invariants and idempotency. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0948 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0950 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Implement the frontend foundation — Accessibility, performance and reliability hardening | Implement the frontend foundation for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: typed frontend module | The UI uses shared components, server data and route-level boundaries. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0949 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0951 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Implement the happy path — Accessibility, performance and reliability hardening | Implement the happy path for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: working end-to-end primary flow | A representative user completes the intended outcome without manual data edits. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0950 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0952 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Implement non-happy states — Accessibility, performance and reliability hardening | Implement non-happy states for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: loading, empty, stale, offline and error states | Every failure has truthful messaging and a safe recovery action. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0951 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0953 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Add audit and observability — Accessibility, performance and reliability hardening | Add audit and observability for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: logs, audit events and metrics | Correlated events expose failures without leaking sensitive information. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0952 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0954 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Apply security and privacy controls — Accessibility, performance and reliability hardening | Apply security and privacy controls for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: threat-control implementation | Least privilege, data minimization, abuse controls and secret boundaries pass review. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0953 | Quality and Security Lead | P1 | Development / preview | No | Not started
TASK-0955 | P16 — Security, privacy, accessibility and reliability | Accessibility, performance and reliability hardening | Write unit tests — Accessibility, performance and reliability hardening | Write unit tests for Accessibility, performance and reliability hardening. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Accessibility, performance and reliability hardening: unit test suite | Domain rules and boundary conditions fail before the fix and pass after it. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0954, TASK-0935 | Quality and Security Lead | P0 | Development / preview | Yes | Not started
TASK-0956 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Define the release test charter — End-to-end QA and release evidence | Define the release test charter for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: release test charter | Scope, risk, environments and evidence requirements are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0955 | Release Manager | P1 | Local / design | No | Not started
TASK-0957 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Prepare deterministic test data — End-to-end QA and release evidence | Prepare deterministic test data for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: synthetic test dataset | Buyer, seller, property, listing, money and exception data are reproducible. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0956 | Release Manager | P1 | Local / design | No | Not started
TASK-0958 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Validate source and build reproducibility — End-to-end QA and release evidence | Validate source and build reproducibility for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: clean-build evidence | A clean checkout installs, migrates, builds and starts deterministically. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0957 | Release Manager | P1 | Local / design | No | Not started
TASK-0959 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Run complete role and RLS testing — End-to-end QA and release evidence | Run complete role and RLS testing for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: authorization test report | Anonymous and every role pass positive and negative access tests. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0958 | Release Manager | P1 | Local / design | No | Not started
TASK-0960 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Run buyer end-to-end journeys — End-to-end QA and release evidence | Run buyer end-to-end journeys for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: buyer journey report | Search through arrival and support paths pass across breakpoints. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0959 | Release Manager | P1 | Local / design | No | Not started
TASK-0961 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Run seller end-to-end journeys — End-to-end QA and release evidence | Run seller end-to-end journeys for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: seller journey report | Submission through payout and exception paths pass. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0960 | Release Manager | P1 | Local / design | No | Not started
TASK-0962 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Run operations end-to-end journeys — End-to-end QA and release evidence | Run operations end-to-end journeys for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: operations journey report | Review, decision, finance and emergency controls pass. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0961 | Release Manager | P1 | Local / design | No | Not started
TASK-0963 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Run concurrency and idempotency testing — End-to-end QA and release evidence | Run concurrency and idempotency testing for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: concurrency report | Duplicate purchase, webhook, refund and payout effects are prevented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0962 | Release Manager | P1 | Local / design | No | Not started
TASK-0964 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Run accessibility conformance testing — End-to-end QA and release evidence | Run accessibility conformance testing for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: accessibility test report | Automated and manual keyboard and screen-reader issues are resolved. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0963 | Release Manager | P1 | Local / design | No | Not started
TASK-0965 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Run performance and capacity testing — End-to-end QA and release evidence | Run performance and capacity testing for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: performance report | Core Web Vitals and pilot load targets pass. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0964 | Release Manager | P1 | Local / design | No | Not started
TASK-0966 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Run security and abuse testing — End-to-end QA and release evidence | Run security and abuse testing for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: security test report | Critical findings are resolved or launch-blocked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0965 | Release Manager | P1 | Local / design | No | Not started
TASK-0967 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Run dependency failure and recovery drills — End-to-end QA and release evidence | Run dependency failure and recovery drills for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: resilience drill evidence | Payment, map, email, realtime and storage failures recover safely. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0966 | Release Manager | P1 | Local / design | No | Not started
TASK-0968 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Complete pilot user acceptance — End-to-end QA and release evidence | Complete pilot user acceptance for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: UAT evidence | Named scenarios pass with recorded owners and no unresolved launch blocker. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0967 | Release Manager | P1 | Development / preview | No | Not started
TASK-0969 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Rehearse deployment and rollback — End-to-end QA and release evidence | Rehearse deployment and rollback for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: release rehearsal record | Staging deploy, migration, smoke test and rollback succeed. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0968 | Release Manager | P1 | Development / preview | No | Not started
TASK-0970 | P17 — Full-system QA and launch rehearsal | End-to-end QA and release evidence | Pass final pre-production gate — End-to-end QA and release evidence | Pass final pre-production gate for End-to-end QA and release evidence. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | End-to-end QA and release evidence: release candidate approval | All required evidence is linked and release candidate is immutable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0969 | Release Manager | P1 | Development / preview | Yes | Not started
TASK-0971 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Define the release test charter — Support readiness, documentation and launch rehearsal | Define the release test charter for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: release test charter | Scope, risk, environments and evidence requirements are explicit. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0955 | Release Manager | P1 | Local / design | No | Not started
TASK-0972 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Prepare deterministic test data — Support readiness, documentation and launch rehearsal | Prepare deterministic test data for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: synthetic test dataset | Buyer, seller, property, listing, money and exception data are reproducible. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0971 | Release Manager | P1 | Local / design | No | Not started
TASK-0973 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Validate source and build reproducibility — Support readiness, documentation and launch rehearsal | Validate source and build reproducibility for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: clean-build evidence | A clean checkout installs, migrates, builds and starts deterministically. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0972 | Release Manager | P1 | Local / design | No | Not started
TASK-0974 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Run complete role and RLS testing — Support readiness, documentation and launch rehearsal | Run complete role and RLS testing for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: authorization test report | Anonymous and every role pass positive and negative access tests. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0973 | Release Manager | P1 | Local / design | No | Not started
TASK-0975 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Run buyer end-to-end journeys — Support readiness, documentation and launch rehearsal | Run buyer end-to-end journeys for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: buyer journey report | Search through arrival and support paths pass across breakpoints. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0974 | Release Manager | P1 | Local / design | No | Not started
TASK-0976 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Run seller end-to-end journeys — Support readiness, documentation and launch rehearsal | Run seller end-to-end journeys for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: seller journey report | Submission through payout and exception paths pass. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0975 | Release Manager | P1 | Local / design | No | Not started
TASK-0977 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Run operations end-to-end journeys — Support readiness, documentation and launch rehearsal | Run operations end-to-end journeys for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: operations journey report | Review, decision, finance and emergency controls pass. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0976 | Release Manager | P1 | Local / design | No | Not started
TASK-0978 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Run concurrency and idempotency testing — Support readiness, documentation and launch rehearsal | Run concurrency and idempotency testing for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: concurrency report | Duplicate purchase, webhook, refund and payout effects are prevented. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0977 | Release Manager | P1 | Local / design | No | Not started
TASK-0979 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Run accessibility conformance testing — Support readiness, documentation and launch rehearsal | Run accessibility conformance testing for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: accessibility test report | Automated and manual keyboard and screen-reader issues are resolved. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0978 | Release Manager | P1 | Local / design | No | Not started
TASK-0980 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Run performance and capacity testing — Support readiness, documentation and launch rehearsal | Run performance and capacity testing for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: performance report | Core Web Vitals and pilot load targets pass. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0979 | Release Manager | P1 | Local / design | No | Not started
TASK-0981 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Run security and abuse testing — Support readiness, documentation and launch rehearsal | Run security and abuse testing for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: security test report | Critical findings are resolved or launch-blocked. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0980 | Release Manager | P1 | Local / design | No | Not started
TASK-0982 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Run dependency failure and recovery drills — Support readiness, documentation and launch rehearsal | Run dependency failure and recovery drills for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: resilience drill evidence | Payment, map, email, realtime and storage failures recover safely. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0981 | Release Manager | P1 | Local / design | No | Not started
TASK-0983 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Complete pilot user acceptance — Support readiness, documentation and launch rehearsal | Complete pilot user acceptance for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: UAT evidence | Named scenarios pass with recorded owners and no unresolved launch blocker. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0982 | Release Manager | P1 | Development / preview | No | Not started
TASK-0984 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Rehearse deployment and rollback — Support readiness, documentation and launch rehearsal | Rehearse deployment and rollback for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: release rehearsal record | Staging deploy, migration, smoke test and rollback succeed. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0983 | Release Manager | P1 | Development / preview | No | Not started
TASK-0985 | P17 — Full-system QA and launch rehearsal | Support readiness, documentation and launch rehearsal | Pass final pre-production gate — Support readiness, documentation and launch rehearsal | Pass final pre-production gate for Support readiness, documentation and launch rehearsal. Preserve StayRelay's evidence-backed reservation-transfer model and do not substitute a generic booking-site pattern. | Support readiness, documentation and launch rehearsal: release candidate approval | All required evidence is linked and release candidate is immutable. Evidence is linked, the authoritative state is server-confirmed, and no unresolved critical issue is hidden. | TASK-0984, TASK-0970 | Release Manager | P1 | Development / preview | Yes | Not started
TASK-0986 | P18 — Production launch and monitored operations | Production launch | Freeze the production release candidate | Tag immutable application, migration and asset versions after every launch gate passes | Release candidate tag and checksums | No unreviewed change can enter the launch candidate | TASK-0985 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0987 | P18 — Production launch and monitored operations | Production launch | Confirm production accounts, domains and ownership | Verify Vercel, Supabase, payment, Google, email, HubSpot, DNS and monitoring ownership | Production ownership record | Every production service has a verified owner and recovery path | TASK-0986 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0988 | P18 — Production launch and monitored operations | Production launch | Install and validate production secrets | Configure restricted production secrets without exposing them to code, logs or client bundles | Secret validation evidence | All required secrets pass safe connection tests and rotation ownership is recorded | TASK-0987 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0989 | P18 — Production launch and monitored operations | Production launch | Create and verify production backups | Take pre-launch backups and prove restore procedures in an isolated environment | Backup and restore evidence | Database and critical configuration can be restored within the target | TASK-0988 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0990 | P18 — Production launch and monitored operations | Production launch | Apply reviewed production database migrations | Apply the immutable migration set with monitoring and rollback controls | Production migration record | Migration head matches the release and integrity checks pass | TASK-0989 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0991 | P18 — Production launch and monitored operations | Production launch | Deploy the production application | Deploy the approved build and bind production services without enabling public traffic | Production deployment ID | The deployed build matches the release candidate exactly | TASK-0990 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0992 | P18 — Production launch and monitored operations | Production launch | Run private production smoke tests | Test authentication, role boundaries, search, seller submission, operations and sandbox-safe transaction paths | Production smoke report | Critical private smoke scenarios pass with no real unintended transaction | TASK-0991 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0993 | P18 — Production launch and monitored operations | Production launch | Validate production maps, media and destination themes | Confirm destinations select correct coordinates, imagery, palettes, fallbacks and responsive assets | Production visual validation | Location changes propagate consistently without layout, licensing or privacy defects | TASK-0992 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0994 | P18 — Production launch and monitored operations | Production launch | Validate production payment and webhook readiness | Complete provider-approved low-risk verification of signatures, idempotency, reconciliation and alerting | Payment readiness evidence | No browser path can create authoritative paid state and all provider events reconcile | TASK-0993 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0995 | P18 — Production launch and monitored operations | Production launch | Seed only approved pilot data | Load reviewed properties, policies, destination profiles and eligible inventory for the controlled pilot | Approved production seed record | No demo, invented or unverified listing becomes bookable | TASK-0994 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0996 | P18 — Production launch and monitored operations | Production launch | Activate production monitoring and on-call | Enable dashboards, alerts, incident contacts, support queues and emergency pause | Monitoring and on-call evidence | Critical failures alert the responsible owner and emergency controls are tested | TASK-0995 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0997 | P18 — Production launch and monitored operations | Production launch | Complete final founder and accountable-owner launch approval | Present evidence for legal, finance, provider, security, operations and product launch gates | Signed launch approval | Every mandatory gate is approved by its accountable owner | TASK-0996 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0998 | P18 — Production launch and monitored operations | Production launch | Open controlled public traffic | Enable the approved domain and pilot traffic limits with feature flags and rate controls | Public launch event record | Real users can access only the approved pilot scope | TASK-0997 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-0999 | P18 — Production launch and monitored operations | Production launch | Verify the first live end-to-end production journey | Complete a founder-approved controlled real journey from discovery through the furthest legally approved stage | Live journey evidence | Browser, API, data, operations and notifications agree on the same authoritative state | TASK-0998 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-1000 | P18 — Production launch and monitored operations | Production launch | Open the controlled production beta | Confirm the public site, buyer and seller workspaces, private operations console, maps, approved imagery, transactions, support, monitoring and rollback are operating under controlled traffic | Controlled production beta handoff | StayRelay is publicly usable within the approved pilot, rollback is ready, owners are monitoring and the final 100-task quality certification can begin | TASK-0999 | Founder and Release Manager | P0 | Production | Yes | Not started
TASK-1001 | P19 — Final design, page and production certification | Typography and visual-system certification | Audit every loaded font and remove inconsistent families | Inventory CSS, components, emails and generated documents for font-family drift | Font inventory and removal PR | Only the approved typography families and fallbacks remain | TASK-1000 | Design Systems Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1002 | P19 — Final design, page and production certification | Typography and visual-system certification | Adopt the final modern type stack | Use Inter Variable for product UI and Newsreader Variable only for large editorial destination headings, subject to licence verification | Typography ADR and token update | The choice is licensed, legible and consistent with the audited design direction | TASK-1001 | Design Systems Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1003 | P19 — Final design, page and production certification | Typography and visual-system certification | Self-host and subset production font files | Create minimal WOFF2 Latin and required Indian-language subsets without third-party runtime tracking | Optimized self-hosted font package | Each required script renders and unused glyph weight is removed | TASK-1002 | Design Systems Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1004 | P19 — Final design, page and production certification | Typography and visual-system certification | Configure font preload and fallback metrics | Preload only critical faces and tune fallback metrics to prevent visible layout shift | Font-loading implementation | Text appears immediately and font swap does not move critical layout | TASK-1003 | Design Systems Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1005 | P19 — Final design, page and production certification | Typography and visual-system certification | Define the complete type scale | Specify display, H1, H2, H3, body, label, caption, button, price, data and legal text tokens | Responsive typography scale | Every screen uses semantic tokens rather than one-off sizes | TASK-1004 | Design Systems Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1006 | P19 — Final design, page and production certification | Typography and visual-system certification | Tune typography for mobile and ultra-wide screens | Set fluid clamps, line lengths, wrapping and line heights for all supported breakpoints | Responsive type implementation | Headlines remain expressive and body text remains readable without clipping | TASK-1005 | Design Systems Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1007 | P19 — Final design, page and production certification | Typography and visual-system certification | Tune numbers, dates, prices and operational data | Apply tabular numerals, currency alignment and dense-table rules where precision matters | Numeric typography specification | Money, dates, IDs and status values align and scan correctly | TASK-1006 | Design Systems Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1008 | P19 — Final design, page and production certification | Typography and visual-system certification | Verify multilingual glyph coverage | Test English, Hindi, Telugu and every approved pilot language with real strings | Glyph coverage report | No tofu glyph, broken shaping or inappropriate fallback is visible | TASK-1007 | Design Systems Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1009 | P19 — Final design, page and production certification | Typography and visual-system certification | Run typography accessibility and zoom testing | Check 200 percent zoom, browser text enlargement, contrast and long translations | Typography accessibility evidence | No essential content clips, overlaps or becomes unreadable | TASK-1008 | Design Systems Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1010 | P19 — Final design, page and production certification | Typography and visual-system certification | Approve the production typography system | Review real pages at mobile, tablet, desktop and ultra-wide sizes | Signed typography acceptance | Design, accessibility and engineering approve the final rendered type system | TASK-1009 | Design Systems Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1011 | P19 — Final design, page and production certification | Home page and public storytelling certification | Rebuild the main hero around the actual StayRelay idea | Create an image-led hero explaining that verified eligible reservations can find a new traveller | Production home hero | A first-time visitor understands the two-sided product within five seconds | TASK-1010 | Brand and Growth Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1012 | P19 — Final design, page and production certification | Home page and public storytelling certification | Create buyer, seller and professional admin entry points | Present Find a stay and Sell a booking as equal primary paths and add a polished Admin Access control in the main navigation | Three-path entry system | Buyer and seller paths open the correct journey; Admin Access opens only the hardened dedicated admin login | TASK-1011 | Brand and Growth Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1013 | P19 — Final design, page and production certification | Home page and public storytelling certification | Polish the floating search experience | Refine destination, dates, guests and radius with strong focus, keyboard and mobile behavior | Production search composer | Search feels immediate and validates without ambiguity | TASK-1012 | Brand and Growth Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1014 | P19 — Final design, page and production certification | Home page and public storytelling certification | Implement the destination-transforming home state | After a confirmed place selection, change hero, local copy, imagery, map context and relevant modules | Dynamic home theme | The selected destination is obvious and persists without a wrong-city flash | TASK-1013 | Brand and Growth Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1015 | P19 — Final design, page and production certification | Home page and public storytelling certification | Build the verified-stay discovery rail | Show truthful eligible inventory or an honest high-quality empty state | Live stay rail | No fictional result appears bookable and card imagery is authorised | TASK-1014 | Brand and Growth Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1016 | P19 — Final design, page and production certification | Home page and public storytelling certification | Create the Reservation Passport story module | Explain evidence, transfer progress and arrival readiness visually | Passport explainer | Users understand what the Passport proves and what it does not | TASK-1015 | Brand and Growth Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1017 | P19 — Final design, page and production certification | Home page and public storytelling certification | Create the seller value and process module | Explain submission, verification, pricing, transfer and payout without unrealistic promises | Seller journey section | A seller knows the next action, timing and conditions | TASK-1016 | Brand and Growth Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1018 | P19 — Final design, page and production certification | Home page and public storytelling certification | Create protection, trust and limitation content | Show process-based trust, support and material limitations without invented claims | Protection section | All statements are backed by approved policy | TASK-1017 | Brand and Growth Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1019 | P19 — Final design, page and production certification | Home page and public storytelling certification | Complete public footer, help and legal navigation | Add accessible links, contact routes, pilot coverage, terms, privacy and status | Production public footer | Users can reach support and required legal information from every public page | TASK-1018 | Brand and Growth Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1020 | P19 — Final design, page and production certification | Home page and public storytelling certification | Approve the complete public-site experience | Run visual, copy, responsive, accessibility and conversion review across public routes | Public-site acceptance evidence | No public page is dull, empty, misleading, inconsistent or disconnected | TASK-1019 | Brand and Growth Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1021 | P19 — Final design, page and production certification | Buyer workspace and transaction-page certification | Certify buyer onboarding and workspace entry | Test account creation, destination intent, preferences and workspace switching | Buyer onboarding evidence | A new buyer reaches useful inventory without confusion | TASK-1020 | Buyer Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1022 | P19 — Final design, page and production certification | Buyer workspace and transaction-page certification | Certify search, filters, sort and radius behavior | Test exact dates, guests, accommodation type, price, readiness, distance and 100 km expansion | Buyer search evidence | List and map return the same eligible records | TASK-1021 | Buyer Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1023 | P19 — Final design, page and production certification | Buyer workspace and transaction-page certification | Certify listing cards and image fallbacks | Review card hierarchy, authorised photos, totals, dates, distance and availability states | Listing-card acceptance | Cards are visually premium and transactionally truthful | TASK-1022 | Buyer Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1024 | P19 — Final design, page and production certification | Buyer workspace and transaction-page certification | Certify canonical property pages | Review galleries, maps, amenities, local context and separation from exact reservation offers | Property-page acceptance | General property facts never replace listing-specific terms | TASK-1023 | Buyer Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1025 | P19 — Final design, page and production certification | Buyer workspace and transaction-page certification | Certify exact listing detail pages | Review gallery, Passport summary, terms, fees, dates, room and transfer expectations | Listing-detail acceptance | All purchase-critical information is visible before checkout | TASK-1024 | Buyer Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1026 | P19 — Final design, page and production certification | Buyer workspace and transaction-page certification | Certify checkout review and guest forms | Test validation, autosave, back navigation, consent, expiry and accessibility | Checkout UX evidence | A buyer completes checkout without lost state or duplicate action | TASK-1025 | Buyer Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1027 | P19 — Final design, page and production certification | Buyer workspace and transaction-page certification | Certify payment and uncertain-result screens | Review processing, success, failure, cancellation, expiry and uncertainty recovery | Payment UX evidence | The browser never invents paid status | TASK-1026 | Buyer Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1028 | P19 — Final design, page and production certification | Buyer workspace and transaction-page certification | Certify My stays, receipts and saved stays | Review empty, active, historical, cancelled, refunded and claimed states | Buyer account acceptance | Every buyer record resolves to authoritative server state | TASK-1027 | Buyer Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1029 | P19 — Final design, page and production certification | Buyer workspace and transaction-page certification | Certify Passport, transfer and arrival experiences | Test milestone clarity, tasks, safe address release, maps and support escalation | Fulfilment UX evidence | A buyer knows what has happened and what to do next | TASK-1028 | Buyer Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1030 | P19 — Final design, page and production certification | Buyer workspace and transaction-page certification | Approve the complete buyer experience | Run full buyer journeys on real devices and supported browsers | Signed buyer acceptance | No buyer P0 or P1 usability, state or visual defect remains | TASK-1029 | Buyer Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1031 | P19 — Final design, page and production certification | Seller workspace and evidence-flow certification | Certify seller onboarding and eligibility education | Test seller intent, limitations, responsibilities and workspace switching | Seller onboarding evidence | Sellers understand that submission is not automatic approval | TASK-1030 | Seller Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1032 | P19 — Final design, page and production certification | Seller workspace and evidence-flow certification | Certify property search and accommodation classification | Test Google place selection, manual correction, canonical matching and separate source channel | Property-entry evidence | Hotel, villa and apartment remain accommodation types while Airbnb remains a source | TASK-1031 | Seller Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1033 | P19 — Final design, page and production certification | Seller workspace and evidence-flow certification | Certify reservation basics and date handling | Test check-in, check-out, timezone, guests, rooms and confirmation identifiers | Reservation-entry evidence | Impossible dates and ambiguous local times are rejected clearly | TASK-1032 | Seller Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1034 | P19 — Final design, page and production certification | Seller workspace and evidence-flow certification | Certify rate, payment and cancellation input | Test price, taxes, amount paid, amount due, rate plan and policy fields | Rate-input evidence | Seller claims are distinguished from verified evidence | TASK-1033 | Seller Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1035 | P19 — Final design, page and production certification | Seller workspace and evidence-flow certification | Certify private evidence upload | Test drag-and-drop, mobile capture, progress, scanning, retry, privacy and deletion rules | Upload acceptance | Sensitive evidence remains private and recoverable from failure | TASK-1034 | Seller Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1036 | P19 — Final design, page and production certification | Seller workspace and evidence-flow certification | Certify extraction review and correction | Test OCR or AI draft highlighting, seller confirmation and conflict display | Extraction-review evidence | Automated output never becomes a verified fact by itself | TASK-1035 | Seller Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1037 | P19 — Final design, page and production certification | Seller workspace and evidence-flow certification | Certify verification-status communication | Review needs-information, ineligible, risk-pending and ready-to-price states | Seller-status acceptance | Every status has a reason and a safe next action | TASK-1036 | Seller Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1038 | P19 — Final design, page and production certification | Seller workspace and evidence-flow certification | Certify pricing, proceeds and listing preview | Review fees, expiry, net proceeds, imagery and public-copy preview | Seller pricing evidence | Displayed proceeds and listing data come from the active server versions | TASK-1037 | Seller Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1039 | P19 — Final design, page and production certification | Seller workspace and evidence-flow certification | Certify listing management, transfer and payout views | Test pause, material edit invalidation, transfer tasks, claims and payout gates | Seller management evidence | Seller actions immediately and safely affect buyer availability | TASK-1038 | Seller Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1040 | P19 — Final design, page and production certification | Seller workspace and evidence-flow certification | Approve the complete seller experience | Run first-time and returning seller journeys across breakpoints | Signed seller acceptance | No seller P0 or P1 usability, privacy, state or visual defect remains | TASK-1039 | Seller Product Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1041 | P19 — Final design, page and production certification | Operations, administration and finance certification | Certify public Admin Access entry and protected admin authentication | Test the homepage Admin Access control, dedicated admin login, generic errors, MFA, session expiry, direct URLs and role denial | Admin access and isolation evidence | The entry is professional and visible, but no customer or unauthorised user can register as admin or access protected data | TASK-1040 | Operations Platform Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1042 | P19 — Final design, page and production certification | Operations, administration and finance certification | Certify evidence-review queues | Test sorting, ownership, SLA, missing evidence, conflict and duplicate workflows | Evidence-queue acceptance | Reviewers can resolve work without editing raw state | TASK-1041 | Operations Platform Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1043 | P19 — Final design, page and production certification | Operations, administration and finance certification | Certify policy and eligibility decisions | Test sources, versions, reason codes, expiry and exact-reservation binding | Eligibility operations evidence | Unknown or stale evidence cannot produce sellable inventory | TASK-1042 | Operations Platform Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1044 | P19 — Final design, page and production certification | Operations, administration and finance certification | Certify risk and capital approval | Test exposure limits, reserve availability, segregation and invalidation | Risk operations evidence | Risk approval remains separate from eligibility | TASK-1043 | Operations Platform Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1045 | P19 — Final design, page and production certification | Operations, administration and finance certification | Certify property catalogue and media moderation | Test match, merge, split, aliases, map pins, rights and rejection | Catalogue operations evidence | Canonical records and media provenance remain auditable | TASK-1044 | Operations Platform Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1046 | P19 — Final design, page and production certification | Operations, administration and finance certification | Certify order, payment and reconciliation controls | Test provider events, uncertain states, ledger balance and manual review | Finance operations evidence | Every money status reconciles to immutable entries | TASK-1045 | Operations Platform Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1047 | P19 — Final design, page and production certification | Operations, administration and finance certification | Certify transfer, arrival and exception queues | Test overdue tasks, pre-arrival rechecks, check-in failures and escalation | Fulfilment operations evidence | Operations can identify and resolve every exception | TASK-1046 | Operations Platform Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1048 | P19 — Final design, page and production certification | Operations, administration and finance certification | Certify claims, refunds, recovery and payout controls | Test evidence, decisions, approvals, holds, retries and segregation | Claims and payout evidence | Refund, recovery and payout remain distinct controlled processes | TASK-1047 | Operations Platform Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1049 | P19 — Final design, page and production certification | Operations, administration and finance certification | Certify audit logs, feature flags and emergency pause | Test before-and-after history, reason codes, flags and kill switches | Platform-control evidence | High-impact actions are attributable and reversible where designed | TASK-1048 | Operations Platform Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1050 | P19 — Final design, page and production certification | Operations, administration and finance certification | Approve the complete operations experience | Run role-specific desktop workflows with realistic queue volumes | Signed operations acceptance | No operations P0 or P1 control, clarity or performance defect remains | TASK-1049 | Operations Platform Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1051 | P19 — Final design, page and production certification | Support, content, legal pages and communications certification | Design and certify the support landing page | Create clear issue categories, urgent help, self-service and case entry | Production support home | A user can identify the correct support path in one decision | TASK-1050 | Customer Operations Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1052 | P19 — Final design, page and production certification | Support, content, legal pages and communications certification | Certify authenticated support-case creation | Test order-linked, listing-linked and general cases with privacy-safe attachments | Support intake evidence | Cases retain context without exposing unrelated records | TASK-1051 | Customer Operations Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1053 | P19 — Final design, page and production certification | Support, content, legal pages and communications certification | Certify support-case tracking and replies | Test status, messages, response expectations, closure and reopening | Support tracking evidence | Buyer and seller see accurate case progress | TASK-1052 | Customer Operations Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1054 | P19 — Final design, page and production certification | Support, content, legal pages and communications certification | Certify the help-centre information architecture | Organize buyer, seller, transfer, payment, arrival, claims and account articles | Help-centre structure | Users reach the correct article through search and navigation | TASK-1053 | Customer Operations Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1055 | P19 — Final design, page and production certification | Support, content, legal pages and communications certification | Certify contextual help across every core page | Add precise help links beside confusing or high-risk actions | Contextual-help implementation | Help opens without losing form or transaction state | TASK-1054 | Customer Operations Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1056 | P19 — Final design, page and production certification | Support, content, legal pages and communications certification | Certify terms, privacy, cookies and protection pages | Verify current versions, consent links, dates, readability and evidence owners | Legal-page acceptance | No draft or unsupported legal claim is presented as approved | TASK-1055 | Customer Operations Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1057 | P19 — Final design, page and production certification | Support, content, legal pages and communications certification | Certify transactional email templates | Review identity, hierarchy, mobile rendering, links, expiry and sensitive-data minimization | Email-template evidence | Every critical state has a truthful accessible email | TASK-1056 | Customer Operations Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1058 | P19 — Final design, page and production certification | Support, content, legal pages and communications certification | Certify SMS and approved messaging templates | Review concise content, consent, opt-out, deep links and fallback | Messaging-template evidence | No channel leaks private evidence or exact address early | TASK-1057 | Customer Operations Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1059 | P19 — Final design, page and production certification | Support, content, legal pages and communications certification | Certify notification preferences and delivery history | Test required versus optional messages, retries, failures and user controls | Notification-centre evidence | Users can understand and control permitted communications | TASK-1058 | Customer Operations Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1060 | P19 — Final design, page and production certification | Support, content, legal pages and communications certification | Approve support and communications readiness | Run timed support drills and verify owner coverage | Signed support acceptance | Support can operate from launch with tested escalation paths | TASK-1059 | Customer Operations Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1061 | P19 — Final design, page and production certification | Destination imagery and dynamic-theme certification | Reconcile all 140 image registry entries | Recover supplied prompts, remove duplicates and assign stable asset IDs | Completed 140-asset registry | Every source prompt is accounted for or explicitly marked missing | TASK-1060 | Creative Technology Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1062 | P19 — Final design, page and production certification | Destination imagery and dynamic-theme certification | Certify destination hero images | Review plausibility, cultural accuracy, rights, focal point and responsive crops | Approved destination hero set | Each launch destination has a premium truthful hero and fallback | TASK-1061 | Creative Technology Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1063 | P19 — Final design, page and production certification | Destination imagery and dynamic-theme certification | Certify property and listing photography | Verify ownership, moderation, sequence, duplicate detection and truthfulness | Approved property media set | Generated editorial art never appears as real inventory | TASK-1062 | Creative Technology Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1064 | P19 — Final design, page and production certification | Destination imagery and dynamic-theme certification | Certify page-slot image mapping | Validate home, cards, property, listing, checkout, Passport, seller and support slots | Image-slot mapping evidence | Every slot loads the intended asset class and nothing else | TASK-1063 | Creative Technology Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1065 | P19 — Final design, page and production certification | Destination imagery and dynamic-theme certification | Certify theme tokens for each destination | Review semantic colours, contrast, backgrounds, accents and seasonal variants | Destination theme profiles | Destination styling remains recognizably StayRelay and accessible | TASK-1064 | Creative Technology Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1066 | P19 — Final design, page and production certification | Destination imagery and dynamic-theme certification | Certify theme persistence across routes | Test URL, server rendering, refresh, back button, tabs and workspace switching | Theme-persistence evidence | No page flashes or inherits the wrong destination | TASK-1065 | Creative Technology Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1067 | P19 — Final design, page and production certification | Destination imagery and dynamic-theme certification | Certify image loading and fallbacks | Test slow network, missing CDN object, rejected media, offline and disabled images | Image-fallback evidence | Layout and meaning remain complete without imagery | TASK-1066 | Creative Technology Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1068 | P19 — Final design, page and production certification | Destination imagery and dynamic-theme certification | Certify responsive crops and art direction | Review mobile portrait, card landscape, desktop hero and social preview crops | Responsive art-direction evidence | The subject remains clear at every breakpoint | TASK-1067 | Creative Technology Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1069 | P19 — Final design, page and production certification | Destination imagery and dynamic-theme certification | Certify media performance and caching | Measure LCP, bytes, decode time, cache headers and invalidation | Media performance report | Image-led pages meet the production performance budget | TASK-1068 | Creative Technology Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1070 | P19 — Final design, page and production certification | Destination imagery and dynamic-theme certification | Approve the complete visual asset system | Review every published asset in its real page context | Signed visual-asset acceptance | No rights, truthfulness, quality, accessibility or performance blocker remains | TASK-1069 | Creative Technology Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1071 | P19 — Final design, page and production certification | Responsive, accessibility and performance certification | Certify small mobile layouts | Test 320 to 390 pixel widths, touch targets, keyboards, sheets and safe areas | Small-mobile evidence | Every primary task completes without horizontal scrolling | TASK-1070 | Quality Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1072 | P19 — Final design, page and production certification | Responsive, accessibility and performance certification | Certify large mobile and tablet layouts | Test portrait and landscape navigation, maps, tables and modals | Tablet evidence | Content hierarchy and interaction remain intentional | TASK-1071 | Quality Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1073 | P19 — Final design, page and production certification | Responsive, accessibility and performance certification | Certify laptop and desktop layouts | Test common browser zoom and window sizes with realistic long content | Desktop evidence | No clipped controls, excessive empty space or unreadable line length remains | TASK-1072 | Quality Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1074 | P19 — Final design, page and production certification | Responsive, accessibility and performance certification | Certify ultra-wide behavior | Test bounded content, maps, galleries and operations density above 1920 pixels | Ultra-wide evidence | Content does not stretch into low-density empty canvases | TASK-1073 | Quality Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1075 | P19 — Final design, page and production certification | Responsive, accessibility and performance certification | Complete keyboard-only certification | Traverse every public, buyer, seller and operations flow without a pointer | Keyboard evidence | Focus order, traps, skip links and dialogs behave correctly | TASK-1074 | Quality Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1076 | P19 — Final design, page and production certification | Responsive, accessibility and performance certification | Complete screen-reader certification | Test landmarks, headings, forms, tables, status changes and errors | Screen-reader evidence | Critical flows are understandable with supported assistive technology | TASK-1075 | Quality Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1077 | P19 — Final design, page and production certification | Responsive, accessibility and performance certification | Complete contrast, motion and cognitive review | Test all themes, reduced motion, non-colour cues and plain-language instructions | Inclusive-design evidence | No destination theme or animation reduces access | TASK-1076 | Quality Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1078 | P19 — Final design, page and production certification | Responsive, accessibility and performance certification | Certify Core Web Vitals | Measure LCP, INP and CLS on home, search, listing, checkout and dashboards | Web-vitals report | Every critical route meets the approved production threshold | TASK-1077 | Quality Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1079 | P19 — Final design, page and production certification | Responsive, accessibility and performance certification | Certify runtime performance and memory | Profile map, gallery, long tables, realtime updates and route transitions | Runtime performance evidence | No leak, long task or unnecessary rerender harms primary use | TASK-1078 | Quality Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1080 | P19 — Final design, page and production certification | Responsive, accessibility and performance certification | Approve responsive and inclusive quality | Run final multidisciplinary device lab review | Signed responsive and accessibility acceptance | No P0 or P1 responsive, accessibility or performance issue remains | TASK-1079 | Quality Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1081 | P19 — Final design, page and production certification | Cross-browser, integration and release-candidate certification | Consolidate the canonical release branch | Identify the correct repository history and stop stale preview branches being treated as current | Canonical release branch record | One traceable branch contains the accepted production candidate | TASK-1080 | Release Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1082 | P19 — Final design, page and production certification | Cross-browser, integration and release-candidate certification | Diagnose and resolve failed Vercel previews | Investigate the failed task previews shown in deployment history and fix root causes | Preview failure report and fixes | No required release deployment remains in Error state | TASK-1081 | Release Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1083 | P19 — Final design, page and production certification | Cross-browser, integration and release-candidate certification | Certify Chrome, Safari, Firefox and Edge | Run critical journeys on current supported desktop browsers | Desktop browser matrix | No browser-specific P0 or P1 defect remains | TASK-1082 | Release Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1084 | P19 — Final design, page and production certification | Cross-browser, integration and release-candidate certification | Certify iOS Safari and Android Chrome | Run critical journeys on representative real mobile devices | Mobile browser matrix | Forms, uploads, maps, payments and navigation work reliably | TASK-1083 | Release Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1085 | P19 — Final design, page and production certification | Cross-browser, integration and release-candidate certification | Certify Supabase auth, RLS, storage and realtime | Run positive, negative, reconnect and expired-session tests | Supabase integration evidence | No cross-user leak or stale authoritative state remains | TASK-1084 | Release Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1086 | P19 — Final design, page and production certification | Cross-browser, integration and release-candidate certification | Certify Google Maps and geospatial search | Test autocomplete, geocoding, attribution, pin correction, quotas and 100 km PostGIS results | Maps integration evidence | Maps degrade safely and never invent inventory | TASK-1085 | Release Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1087 | P19 — Final design, page and production certification | Cross-browser, integration and release-candidate certification | Certify payment, CRM and notification integrations | Run sandbox and approved production-readiness tests for every adapter | Integration certification report | Events are signed, deduplicated, monitored and recoverable | TASK-1086 | Release Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1088 | P19 — Final design, page and production certification | Cross-browser, integration and release-candidate certification | Run complete visual regression | Compare every key route, role, theme, breakpoint and state against approved baselines | Visual regression report | Unapproved visual drift is fixed or explicitly accepted | TASK-1087 | Release Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1089 | P19 — Final design, page and production certification | Cross-browser, integration and release-candidate certification | Run full production-candidate regression | Execute the complete automated and manual suite on the immutable candidate | Release-candidate test report | All required suites pass with no hidden retry-only success | TASK-1088 | Release Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1090 | P19 — Final design, page and production certification | Cross-browser, integration and release-candidate certification | Approve the immutable final release candidate | Freeze code, migrations, assets, configuration and evidence after review | Final release candidate tag | The candidate is reproducible and ready for stable promotion | TASK-1089 | Release Engineering Lead | P0 | Production beta / release candidate | Yes | Not started
TASK-1091 | P19 — Final design, page and production certification | Stable-production promotion and final assurance | Promote the certified candidate to stable production | Deploy the immutable candidate using the approved migration and rollout procedure | Stable production deployment | The live build exactly matches the certified tag | TASK-1090 | Founder and Release Manager | P0 | Stable production | Yes | Not started
TASK-1092 | P19 — Final design, page and production certification | Stable-production promotion and final assurance | Run every critical production smoke test | Verify public, buyer, seller, operations, maps, images, support and safe payment states | Stable production smoke report | All critical smoke tests pass against production | TASK-1091 | Founder and Release Manager | P0 | Stable production | Yes | Not started
TASK-1093 | P19 — Final design, page and production certification | Stable-production promotion and final assurance | Verify production fonts and visual assets | Inspect real CDN responses, font files, crops, fallbacks and cache headers | Production visual-delivery evidence | Typography and media match the approved system without CLS | TASK-1092 | Founder and Release Manager | P0 | Stable production | Yes | Not started
TASK-1094 | P19 — Final design, page and production certification | Stable-production promotion and final assurance | Verify production security and privacy controls | Check headers, cookies, RLS, access denial, upload privacy and redacted observability | Production security evidence | No critical exposure is found | TASK-1093 | Founder and Release Manager | P0 | Stable production | Yes | Not started
TASK-1095 | P19 — Final design, page and production certification | Stable-production promotion and final assurance | Verify production money and reconciliation controls | Confirm provider account, webhooks, ledger, refund and payout safeguards | Production finance-control evidence | All enabled money paths reconcile and disabled paths remain blocked | TASK-1094 | Founder and Release Manager | P0 | Stable production | Yes | Not started
TASK-1096 | P19 — Final design, page and production certification | Stable-production promotion and final assurance | Verify production support and incident response | Open controlled test cases, alerts and escalation without contacting unintended users | Support and incident evidence | Owners receive and resolve the test signal within target | TASK-1095 | Founder and Release Manager | P0 | Stable production | Yes | Not started
TASK-1097 | P19 — Final design, page and production certification | Stable-production promotion and final assurance | Verify rollback, backup and emergency pause | Reconfirm restoration points, rollback commands and marketplace pause controls | Final recovery evidence | The team can stop or reverse a damaging release safely | TASK-1096 | Founder and Release Manager | P0 | Stable production | Yes | Not started
TASK-1098 | P19 — Final design, page and production certification | Stable-production promotion and final assurance | Observe the live pilot stability window | Monitor errors, latency, web vitals, conversion, support and transaction consistency | Stability-window report | Metrics remain within approved thresholds for the defined window | TASK-1097 | Founder and Release Manager | P0 | Stable production | Yes | Not started
TASK-1099 | P19 — Final design, page and production certification | Stable-production promotion and final assurance | Resolve final production defects and rerun affected tests | Fix every launch-blocking issue through reviewed changes and refresh evidence | Final defect-closure report | No P0 or P1 issue remains open | TASK-1098 | Founder and Release Manager | P0 | Stable production | Yes | Not started
TASK-1100 | P19 — Final design, page and production certification | Stable-production promotion and final assurance | Declare StayRelay stable, polished and fully monitored | Complete the final founder, design, engineering, security, finance and operations review | TASK-1100 stable-production handoff | The real website is public, visually world-class, operationally complete within scope, supportable, monitored and rollback-ready | TASK-1099 | Founder and Release Manager | P0 | Stable production | Yes | Not started

## Image Registry
140-image prompt recovery, generation and publication registry
Preserve each original prompt before rewriting. Generated editorial imagery must never appear as a real property photo.
Asset ID | Original Prompt Reference | Destination | Page / Route | Slot | Content Class | Real Property? | Source Tool | Rights | Status | Reviewer | Alt Text | Aspect Ratio | File / URL | Notes
IMG-001 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-002 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-003 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-004 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-005 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-006 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-007 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-008 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-009 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-010 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-011 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-012 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-013 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-014 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-015 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-016 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-017 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-018 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-019 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-020 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-021 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-022 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-023 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-024 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-025 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-026 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-027 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-028 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-029 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-030 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-031 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-032 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-033 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-034 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-035 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-036 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-037 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-038 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-039 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-040 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-041 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-042 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-043 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-044 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-045 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-046 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-047 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-048 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-049 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-050 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-051 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-052 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-053 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-054 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-055 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-056 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-057 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-058 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-059 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-060 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-061 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-062 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-063 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-064 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-065 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-066 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-067 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-068 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-069 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-070 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-071 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-072 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-073 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-074 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-075 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-076 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-077 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-078 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-079 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-080 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-081 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-082 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-083 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-084 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-085 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-086 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-087 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-088 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-089 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-090 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-091 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-092 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-093 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-094 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-095 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-096 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-097 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-098 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-099 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-100 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-101 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-102 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-103 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-104 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-105 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-106 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-107 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-108 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-109 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-110 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-111 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-112 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-113 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-114 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-115 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-116 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-117 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-118 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-119 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-120 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-121 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-122 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-123 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-124 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-125 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-126 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-127 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-128 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-129 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-130 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-131 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-132 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-133 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-134 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-135 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-136 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-137 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-138 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-139 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.
IMG-140 |  |  |  |  | Awaiting classification | No / unknown |  | Unverified | Awaiting prompt audit |  |  |  |  | Recover the original prompt before generation. Do not publish until rights, truthfulness and slot mapping pass review.

## Visual Rules
Location-aware visual behavior
Destination context changes imagery and relevant content while transaction meaning, accessibility and trust remain stable.
Surface | Location-aware behavior | Stable elements | Image source | Fallback | Acceptance criterion
Public home hero | After destination selection, replace the generic hero with the approved destination hero and local context copy. | Logo, primary navigation, search controls and trust language remain stable. | Destination editorial asset, never an unverified property photo. | Neutral StayRelay transfer-concept hero. | Theme changes after a confirmed selection without layout shift or inaccessible contrast.
Public home sections | Curated modules reorder to the selected destination, dates and pilot events. | How it works, protection and policy explanations remain consistent. | Approved destination and event imagery. | Generic pilot destination modules. | No module claims bookable inventory unless a verified listing exists.
Search composer | Selected place name, map context and a restrained destination accent persist. | Field order, labels, validation and keyboard behavior remain stable. | Small destination thumbnail or colour token only. | Brand-neutral search surface. | Selection survives navigation and can be cleared explicitly.
Buyer overview | Destination card, saved search and recent context reflect the active destination. | Account, payments and support modules remain brand-stable. | Approved destination card image. | Neutral recommendations panel. | Changing destination does not modify transaction history.
Search results | Cards and map start around selected coordinates and show only StayRelay inventory. | Filter layout, price treatment and readiness statuses remain stable. | Authorised property photos. | Property-type placeholder. | Map and list return the same eligible listing IDs.
Map view | Map center, bounds, labels and distance calculations use selected coordinates. | Controls, attribution and privacy behavior remain stable. | Map provider tiles and approved markers. | List-only recovery state. | 100 km search comes from PostGIS, not Google inventory.
Canonical property page | Local neighbourhood context and nearby destination imagery reflect the property. | Property facts and evidence provenance remain stable. | Authorised property gallery. | Generic accommodation-type fallback. | No generated image is presented as the real property.
Exact listing detail | Destination banner and property gallery provide context for the selected stay. | Dates, room, fees, transfer terms and Passport remain stable and server-confirmed. | Authorised property images plus safe destination banner. | Generic destination and accommodation fallback. | Visual context never obscures material transaction terms.
Checkout | A compact property or destination thumbnail and selected-place label persist. | Form layout, totals, consent and payment controls never change theme unpredictably. | Exact listing thumbnail. | Neutral thumbnail. | Destination context is visible but transactional readability stays constant.
Payment processing | Only a small stay-context strip reflects the destination. | Payment status, security and recovery UI remain brand-stable. | Listing thumbnail if already approved. | No decorative image. | No full-page imagery or motion distracts from payment state.
Reservation Passport | Property image and destination context identify the stay. | Timeline semantics, colours and authoritative statuses remain stable. | Exact authorised listing image. | Code-native landmark icon. | Status meaning never changes by destination theme.
Transfer tracker | Destination and property context persist in the header. | Task order, deadlines, evidence and support controls remain stable. | Small approved property image. | Neutral transfer illustration. | Location theme cannot imply transfer completion.
Arrival guide | Maps, local imagery, address-release status and destination context are prominent. | Security and exact-address gates remain stable. | Authorised property and destination images. | Neutral map and landmark fallback. | Private addresses remain hidden until the approved stage.
Seller overview | Submitted property imagery and destination appear per reservation card. | Verification, tasks, listing and payout information remain stable. | Seller-authorised property image after moderation. | Property-type placeholder. | Unreviewed uploads cannot become public imagery.
Seller wizard | Property search and destination preview confirm the selected place. | Wizard steps, validation and evidence privacy remain stable. | Provider place thumbnail only if terms permit. | Map pin and generic type illustration. | Property and booking source stay separate fields.
Evidence upload | A restrained property context strip prevents wrong-reservation uploads. | Upload security, privacy and extraction review remain stable. | Approved property thumbnail only. | No decorative image. | Sensitive documents are never used as background imagery.
Seller listing preview | Shows exactly how destination and property assets will appear publicly. | Terms, dates, price and readiness state remain authoritative. | Moderated gallery and destination hero. | Visible generic fallback. | Seller must not publish before all required gates pass.
Operations queues | Destination is a filter and compact identifying column, not a visual theme. | Density, status colours, tables and audit controls remain stable. | Tiny property thumbnail only where useful. | No image. | Operational clarity outranks decorative personalization.
Operations detail | Property map, coordinates and media provenance appear in evidence context. | Decision controls, reason codes and audit history remain stable. | Authorised evidence-bound media. | Map marker only. | Reviewers can inspect provenance before approving media.
Help centre | Destination-specific help can appear for local check-in norms and pilot coverage. | Policy and safety content remains version-controlled. | Approved explanatory editorial imagery. | Brand illustration. | Local copy cannot override transaction-specific terms.
Notifications | Message content may include the property and destination when necessary. | Template layout, sender identity and security language remain stable. | Small authorised thumbnail only in supported channels. | Text-only template. | No sensitive address or evidence appears prematurely.
Share preview | Destination and exact public listing context determine the social card. | Brand, truthful price and availability timestamp remain stable. | Authorised listing image. | Destination fallback card. | Shared cards expire or refresh when availability changes.
Empty results | Shows relevant nearby destination context and radius-expansion options. | It clearly states that no eligible StayRelay listing matched. | Destination editorial image. | Neutral search illustration. | Never fill emptiness with ordinary Google hotels as bookable results.
Location unavailable | Retains typed text and offers retry or manual map selection. | Search cannot silently choose another city. | No image required. | Neutral map illustration. | The user understands what failed and how to recover.
Theme persistence | Store confirmed destination context in the URL and server-backed search state; carry it through relevant routes. | Orders and saved records retain their own immutable property context. | Destination theme profile resolved by ID. | Default brand theme. | SSR and client hydration render the same theme without flashing incorrect content.